## Sheet1
es
[5 empty] | CC | Community Councils in ward |  | CMcL | Craig McLachlan
[5 empty] | AM | Area Manager |  | JMcM | John McMillan
[5 empty] | AP | Area Partnership
[5 empty] | CLD | ELC Community Learning and Development
[5 empty] | CR | Community Reps from wider constituency
[5 empty] | HCDT | Community Development Trust
[5 empty] | HBA | Haddington Business Association
| ACTION PLAN | 2016 |  |  | HDCC | Haddington Community Council
| Last Reviewed | 2016-04-04
| by: | SGibb - Reformating Plan
Status Code
| COMPLETED | Project complete |  |  | AP Budget 2015/16 | £100K | Amenity Services
| ACTIVE | Project in active progress or support mode |  |  |  | £50k | Roads
| DEVELOPMENT | Project in development / discussion phase |  |  |  | £50k | General
Town Centre & Local Economy
Champion: TBC
Ref: | Goal/Aim What do we want for our ward? | What is needed? | How will this be achieved? | Where will this happen in our ward? | Lead/working with | Estimated Cost | Funding Source | Target End Date | Progress update
TC1 | Establish Haddington High Street as "The Best Town Square in Scotland" with a vibrant shopping centre. | Develop Action plan to drive improvements to Haddington Town Centre | Sub Group to be established with represenation from HCDT, HBA, HADAS, NHS, ELC | Haddington | AM / HCDT / HBA / HADAS / NHS / ELC |  |  |  | Next meeting of Town Centre Sub Group is on 21/03/16. New Champion to be identified. Work to begin on redeveloping the Plan.
TC6 | Effectively Market all that Haddington & Lammermuir has to Offer | Improve signage to attractions | Through work of Town Centre Sub Group | Haddington | AM / HCDT / HBA / HADAS / NHS / ELC |  |  |  | 11/12/15 Keith Scott arranging to repaint 5 signs in Town Centre. Cost of £2,500 from HAL AP roads budget.
TC2 | Establish Haddington High Street as "The Best Town Square in Scotland" with a vibrant shopping centre. | Property Audit | Establish locations of types of businesses and properties. | Haddington | AM / HCDT / HBA / HADAS / NHS / ELC
TC3 | Develop and Deliver a successful Access Strategy for Haddington Town Centre | More parking spaces and available bus parking spaces | Work with ELC and SusTRans | Haddington | AM/ ELC / HCDT | £30K | SusTrans |  | Work underway finalising aim of strategy for consultant to move forward.
TC4 | Make the Most of Haddington’s Assets including Buildings and Public Spaces | Promote attractions and assets. | Through work of Town Centre Sub Group | Haddington | AM / HCDT / HBA / HADAS / NHS / ELC |  |  |  | Next meeting of Town Centre Sub Group is on 21/03/16. New Champion to be identified. Work to begin on redeveloping the Plan.
TC5 | Make the Most of Haddington’s Assets including Buildings and Public Spaces | Tourism asset audit to identify what’s there. | Through work of Town Centre Sub Group | Haddington | AM / HCDT / HBA / HADAS / NHS / ELC |  |  |  | Next meeting of Town Centre Sub Group is on 21/03/16. New Champion to be identified. Work to begin on redeveloping the Plan.
Superfast Broadband
Champion: Cllr John McMillan
Ref: | Goal/Aim What do we want for our ward? | What is needed? | How will this be achieved? | Where will this happen in our ward? | Lead/working with | Estimated Cost | Funding Source | Target End Date | Progress update
SB1 | Superfast broadband established throughout the ward | Superfast broadband established throughout the ward | Work with Community Broadband Scotland (CBS)to establish mechanisms for delivering service to rural communities throughout the county. | Across the ward | AM/ELC/CBS |  |  |  | 01/03/16 Meeting with CBS. Indicative timescale agreed. Work underway to develop public consultation. Delay expected around procurement due to State Aid issues. Next meeting scheduled for 29/3
SB2 | Superfast broadband established throughout the areas of the ward out-with the planned roll-out | Develop Plan B: | what can other organisations offer if the current plan cannot move forward. | Across the ward
SB3 | Businesses enabled to take advantage of better broadband access with more home working and more start-ups throughout the ward. | Superfast broadband established throughout the ward |  | Across the ward
Sustainable Travel
Champion: Nick Morgan
Ref: | Goal/Aim What do we want for our ward? | What is needed? | How will this be achieved? | Where will this happen in our ward? | Lead/working with | Estimated Cost | Funding Source | Target End Date | Progress update
ST1 | Increased use of active modes of travel (ie: walking and cycling) for trips within the Ward | Consultation on Local Priorities | Through East Lothian On the Move consultation | Across the ward | ELC Roads; AM; SusTrans, |  | Roads budget and match funding. £10K in total | 2016-03-31 | 10/12/15 Long List of Actions recevied from East Lothian On the Move consultation. To be considered by HAL AP
ST2 | Increased use of active modes of travel (ie: walking and cycling) for trips within the Ward | Install safe cycle storage in Haddington town centre | Install safe cycle storage facilities | Haddington | AM/ELC Roads | 9900 | Roads budget and match funding. £10K in total | 2016-01-31 | 21/01/16 HAL AP agreed to fund installation of 22 cycle stands at 5 locations. Iaiin Reid, ELC advised to proceed with works which are expected to complete by 31/03/16
ST3 | Increased use of active modes of travel (ie: walking and cycling) for trips within the Ward | Ensure all paths have regular benches: | Through East Lothian On the Move consultation | Across the ward | AM/ELC Roads |  | Roads budget and match funding. £10K in total
ST4 | Public Transport provides the ward with reliable, accessible and regular services that meet the community’s needs | Improve community awareness of the services which are available: | By providing comprehensive public transport information in an easily digestible format such as a bus route map, and kept up to date. | Across the ward | AM/ELC
ST5 | Public Transport provides the ward with reliable, accessible and regular services that meet the community’s needs | Allow Garvald residents to use School Bus service to Haddington | Speak to ELC Transportation / Bus provider to explore options | Garvald | AP / ELC / Prentice Coaches |  |  |  | 21/12/15 ELC Transportation / Prentice Coaches advise not possible due to size of vehicle and DDA implications.
ST6 | Creative options are introduces for providing community transport solutions to areas where traditional forms of public transport are not viable. | Establish twice a week services to, Garvald & Morham, and Humbie & Blegbie | Speak to ELC Transportation / Bus provider to explore options | Garvald, Morham, Humbie and Blegbie | AP / ELC
Children and Young People
Champion: Penny Short
Ref: | Goal/Aim What do we want for our ward? | What is needed? | How will this be achieved? | Where will this happen in our ward? | Lead/working with | Estimated Cost | Funding Source | Target End Date | Progress update
YP1 | Children and Young People feel safe in their area: | Mapping unsafe areas. | Consult with young people to establish areas perceived to be unsafe and suggestions on improvements. Execute improvements where possible. | Across the Ward | Area Partnership, ELC, Knox Academy, Youth Reps, Community Learning & Development
YP2 | Children and Young People feel safe in their area: | Improving lighting along dark footpaths. | Establish problem areas and install improvements where possible. | Across the Ward | ELC, Area Partnership, Youth Reps, Pupil Council
YP3 | Children and Young People feel safe in their area: | Police interaction in school to hear young people’s concerns: | Regular police presence in School to hear young people’s concerns. | Across the Ward | Police Service, Knox Academy, Pupil Council, Youth Reps
YP4 | Children and young people can access appropriate facilities and services by sustainable means | Install secure cycle storage at Knox Academy | Install safe storage facilities
YP5 | Children and young people can access appropriate facilities and services by sustainable means | Improve Shower Facilities at Knox Academy | Upgrade facilities | Knox Academy | Knox Academy, FES
YP6 | Children and young people can access appropriate facilities and services by sustainable means | Regular Shuttle-Bus to Haddington for Young People living in villages / rural areas | Provide a regular (perhaps weekly/ fortnightly Fridays) Shuttle-Bus service to take young people into Haddington, and ensuring that attractions and activities are taking place at this time so that young people can play a more active role in their community. | Across the Ward | H&L AP, S Gibb, ELC Transportation, HCDT, The Bridge Centre, Various other attractions throughout Haddington.
YP7 | Children and young people can access appropriate facilities and services by sustainable means | Improve availability of safe active travel routes to school: | Establish areas of demand for shared-use paths to ensure young people have safe cycling and walking routes to access school and other facilities. | Across the Ward | ELC, SusTrans, HAL AP, ELCRP
YP8 | Children have opportunities to play and interact in safe and appropriate environments: | Mobile u12s rural movie night: | Set up a monthly movie night hosted in various villages in the ward showing family friendly films. bonding between young people before high school. | Across the Ward | Area Partnership, Village Hall Committees
YP9 | Children have opportunities to play and interact in safe and appropriate environments: | Multi use play-space at Neilson Park Pavillion: | Refurbish the pavilion in Neilson Park as a multipurpose play space for children and families. | Haddington | Support from the Start; ELPA, HAL AP, FoNP
YP10 | Children have opportunities to play and interact in safe and appropriate environments: | Youth Workers to work with u-12s in the villages in an outdoors environment: | Have youth workers on 6-week blocks overseeing informal play in outdoor spaces | Across the Ward
YP11 | Young people in the ward have spaces to hang out and socialise, and access to high quality recreation facilities: | 50s Diner Style Cafe in Haddington: | Identify facility | Haddington | HCDT, Betty’s Sweet Shop, HDCC, Area Partnership
YP12 | Young people in the ward have spaces to hang out and socialise, and access to high quality recreation facilities: | More opening times for young people at the gym | Establish additional opening times for young people at Aubigny Centre | Haddington | AM/ ELC |  |  |  | 28/10/15 Meeting with Craig Lamb - Aubigny Centre manager. Very keen to support. Need to discuss requirements with Knox Academy pupils
YP13 | Young people in the ward have spaces to hang out and socialise, and access to high quality recreation facilities: | More open-pitch time at Aubigny Astroturf: | Establish additional open-pitch times at Aubigny Astroturf. | Haddington | AM/ELC |  |  |  | 28/10/15 Craig Lamb advises this is not an option due to concerns over users who have to pay for this service
YP14 | Young people in the ward have spaces to hang out and socialise, and access to high quality recreation facilities: | Improvements to Neilson Park | Work with young people to establish improvements to Neilson Park including a Basketball hoop and more seating space. | Haddington | Friends of Neilson Park. H&LAP, Youth Reps, Pupils Councils
YP15 | Young people in the ward have spaces to hang out and socialise, and access to high quality recreation facilities: | Homework Club for Young People | Re-establish Homework Club at the Nungate Centre for students at Knox Academy. | Haddington | Knox Academy, H&LAP, ELC |  |  |  | 26/02/16 - Meeting held with Haddington Football Club who are happy their main hall can be used. SG to meet with S. Ingham @ Knox Academy to discuss on 23/03/16
YP16 | Young people in the ward have spaces to hang out and socialise, and access to high quality recreation facilities: | Provide more places for young people to hang out | Work with young people to establish high quality places throughout the town where young people – particularly S2s – can enjoy hanging out in safety during lunchtimes, evenings and weekends without causing disruption. | Across the Ward | Partnership, Friends of Neilson Park, Haddington and District CC, Youth Reps, Knox Pupil Council, ELC, Bridge Centre
YP17 | Young people in the ward have spaces to hang out and socialise, and access to high quality recreation facilities: | Ensure villages have access to appropriate leisure facilities for young people: | Identify location and provide resources such as table-tennis tables, badminton clubs, etc. | Across the Ward
YP18 | Young people in the ward have spaces to hang out and socialise, and access to high quality recreation facilities: | Ensure there are no barriers to young people booking spaces in the villages and rural parts of the ward | Work with young people and facility operators to encourage use | Across the Ward
YP19 | Young people have a positive, supported experience of education and are able to access guidance and options for their post-school choices. | Training for work schemes supporting local employers to take on young people in the area: | Work with local employers to establish and support internships for school leavers throughout the ward. | Across the Ward | East Lothian Works, Area Partnership, ELC, Local Employers, Haddington Business Association; Bridge Centre
YP20 | Young people have a positive, supported experience of education and are able to access guidance and options for their post-school choices. | Build links with FE/HE providers in the area: | Tie in with QMU and Edinburgh College to ensure young people are aware of HE/FE opportunities within the county and wider area. The Bridge Centre are woking with Knox High to provide free catering and food hygience courses targeted to key areas of the ward and ensuring these provide a "gateway" o courses with Edinburgh College | Across the Ward | HAL AP, QMU, Edinburgh College, Knox, Youth Reps
YP21 | Young people have a positive, supported experience of education and are able to access guidance and options for their post-school choices. | Education for work training at Knox High: | Canon are running training on employment and technical skills within the school, these should continue and be supported where possible. | Across the Ward | Knox High, Area Partnership, Local Employers
YP22 | Ensure Young People have a voice within the H&L Area Partnership | Involve Young People in the work of HAL AP | Engage with Knox Pupil Council and others (Community Councils?) | Across the Ward
Health and Wellbeing
Champion: Gill Colston
Ref: | Goal/Aim What do we want for our ward? | What is needed? | How will this be achieved? | Where will this happen in our ward? | Lead/working with | Estimated Cost | Funding Source | Target End Date | Progress update
HW1 | The ward, and the county are served by an excellent East Lothian Community Hospital at the Roodlands site. | Sufficient Parking at the Hospital / Hospital site should tie in with Active and Public Transport where Possible / Ensure that high quality holistic care services should be rendered in partnership with key third sector agencies, eg: Macmillan Cancer Care, etc. | Work closely with NHS to influence the current and future parking resource / | Haddington | Gill Colston / Ann McCarthy / NHS Lothian |  |  |  | Watching Brief as plans develop. Merger of previous projects HW1/HW2 / HW3
HW4 | There is improved awareness of mental health issues across the community and effective local services | Mental Health Sessions in School | Carry out mental health sessions in schools in a light hearted setting to introduce children to issues around mental health from an early age. | Across the Ward | ELC / NHS Lothian
HW5 | Older people are supported to live independently within their own community for as long as they choose | Identify and implement relevant support measures | Work with Older people and care providers to scope needs | Across the Ward | ELC / NHS Lothian
HW6 | Older people are supported to live independently within their own community for as long as they choose | Develop and support dementia friendly events across the Area | Work with dementia patients and care providers to scope needs | Across the Ward | ELC / NHS Lothian / Dementia Friendly East Lothian |  |  |  | New project
Community Facilities
Champion: Paul Darling
Ref: | Goal/Aim What do we want for our ward? | What is needed? | How will this be achieved? | Where will this happen in our ward? | Lead/working with | Estimated Cost | Funding Source | Target End Date | Progress update
CF1 | Community based clubs, groups and individuals are able to access the facilities that exist within the ward easily and do so regularly. | Community Facilities Audit | Carry out audit of community facilities throughout the ward assessing all facilities for – capacity; current use; opening hours; booking procedure; location | Across the Ward
CF2 | Community based clubs, groups and individuals are able to access the facilities that exist within the ward easily and do so regularly. | Promotion of local facilities and the activities on offer | Through Directory/ What’s On Guide, etc. | Across the Ward
CF3 | All areas of the ward are equipped with the facilities required to support thriving local communities. | Skate Park in Haddington | Work with HDCC to deliver skatepark project | Haddington | AM / HDCC / ELC | 108000 | Various | 2016-06-01 | 03/03/16 Construction works well underway. Expected completion 18/03/16. Official opening 03/06/16
CF4 | All areas of the ward are equipped with the facilities required to support thriving local communities. | Athelstaneford Skatepark: | Majority of funding secured from Viridor, need small amount of additional funding to see project through to completion. | Athelstaneford | Athelstaneford Parent Council |  | Most of funding secured from Viridor. HAL AP agreed to fund £2,297 on 24/6/15 | 2015-12-31 | 22/12/15 skatepark now completed. Awaiting official launch date to be agreed.
CF5 | All areas of the ward are equipped with the facilities required to support thriving local communities. | Utilize Empty Accommodation/ Halls: | Better coordination on how community facilities can be booked: | Across the Ward
CF6 | All areas of the ward are equipped with the facilities required to support thriving local communities. | Improve the park space at the Nungate | Investigate options to encourage wider use | Haddington
CF7 | All areas of the ward are equipped with the facilities required to support thriving local communities. | Assess need for additional facilities in villages, especially for Young People: |  | Across the Ward | Regional CCs, Area Partnership, Local Young Peoples
CF8 | All areas of the ward are equipped with the facilities required to support thriving local communities. | Secure a sustainable future for Fletcher Hall in Saltoun as a key community facility. | Support the local community | Saltoun | ELC
CF9 | Information about facilities and activities within the ward is readily accessible in user friendly formats online and – where appropriate – in print . | Develop Online Facility or App for East Lothian’s Young People: | Potentially hosted through Young Scot website, this would be a portal for Young People in the area with information about transport, events, facilities, job opportunities and further/ higher education opportunities. | Across the Ward | Young Scot
CF10 | Unused buildings are brought back into use, either commercial or community based and play a vital role in community life and the local economy. | Bring the Old School in Gifford back into use: |  | Gifford
Community Safety
Champion: Paul Sales
Ref: | Goal/Aim What do we want for our ward? | What is needed? | How will this be achieved? | Where will this happen in our ward? | Lead/working with | Estimated Cost | Funding Source | Target End Date | Progress update
CS9 | Improved road and pedestrian safety throughout the ward | Speed reduction measures on Whittingehame Drive at the entrance to the football pitches / skatepark | Install speed table with red block paving effect oout early 2016 as agreed with P Forsyth. | Whittingehame Drive, Haddington | ELC Roads | 35000 | Roads | 2016-03-31 | 03/03/2016 Construction expected to commence 07/03/16 and be completed by 31/03/16
CS1 | Improved road and pedestrian safety throughout the ward | A permanent Speed Reactive Sign in East Saltoun | Work with ELC Roads Team to identify solution. | East Saltoun | ELC Roads | 5000 | Roads | 2015-10-31 | 22/12/15 HAL AP agreed funding on 24/6/15. Sign installed and operational October 2015
CS2 | Improved road and pedestrian safety throughout the ward | Effective traffic calming measures in Bolton to address the increase in traffic in the area | Work with ELC Roads Team to identify solution. | Bolton | ELC Roads
CS3 | Improved road and pedestrian safety throughout the ward | Effective traffic calming measures in Humbie to address the increase in traffic in the area | Work with ELC Roads Team to identify solution. | Humbie | ELC Roads
CS4 | Enhanced Community Policing throughout the ward | Focus on prevention rather than reaction. | Integrate the priorities of the Police Scotland ward plan into the Area Plan | Across the Ward | Police Scotland
CS5 | Flood prevention along watercourses is improved. | Improve flood prevention measures at the riverside between Tyne Court and Bridge Street. | Work with ELC Roads Team to identify solution. | Haddington | ELC Roads
CS6 | Reduced incidences of anti-social behaviour in the ward | Proactive multi-agency targetting of Young People to educate and reduce incidences of potential ASB | Communicate with Young People | Across the Ward | ELC | 475 | General | 2016-03-31 | 02/02/16 £475 approved through delegated powers from general fund to pay for CREW 2000 to provide educational talks to pupils at Knox Academy during Feb/March 2016
CS7 | Reduced incidences of substance misuse in the ward | Proactive multi-agency targetting of Young People to educate and reduce incidences of potential ASB | Communicate with Young People | Across the Ward | ELC | 475 | General | 2016-03-31 | 02/02/16 £475 approved through delegated powers from general fund to pay for CREW 2000 to provide educational talks to pupils at Knox Academy during Feb/March 2016
CS8 | People feel safe and secure in their own homes |  |  | Across the Ward
Inclusive Communities
Champion: Rosemary Greenhill
Ref: | Goal/Aim What do we want for our ward? | What is needed? | How will this be achieved? | Where will this happen in our ward? | Lead/working with | Estimated Cost | Funding Source | Target End Date | Progress update
IC1 | That our villages provide residents with access to appropriate and affordable housing where possible in their area. | Revisit Allocation points policy | Work with ELC Housing Team | Across the Ward | AM/ELC
IC2 | That our villages provide residents with access to appropriate and affordable housing where possible in their area. | Allow/ Encourage developments in rural areas which are entirely, or nearly entirely affordable housing. |  | Across the Ward
IC3 | The negative impact of high school catchment boundaries on community cohesion is overcome. | Make representations to the School Catchment Review consultation: Taking place as part of the MIR. |  | Across the Ward
IC4 | The negative impact of high school catchment boundaries on community cohesion is overcome. | Ensure children do not have to travel further than necessary. |  | Across the Ward
IC5 | The negative impact of high school catchment boundaries on community cohesion is overcome. | Assess Boundary Commission review of the ward. |  | Across the Ward
IC6 | Individuals and groups within the local community are able to take practical actions to improve the public realm in their area. | Ensure that the membership of the Area partnership is representative of the whole ward |  | Across the Ward
IC7 | Vulnerable community members are supported in times of severe weather or other crisis. | Support the development of local Resilience plans in each village: | Ensure that community infrastructure is looked at and addressed to ensure the most vulnerable are able to remain in their home community | Across the Ward
IC8 | Each community in our ward has a strong local hub that supports the social needs of residents of all ages. | Support Village Halls as social hubs of Rural Areas: residents. | Ensure village halls are affordable, potentially with discounts for local | Across the Ward
IC9 | Each community in our ward has a strong local hub that supports the social needs of residents of all ages. | Ensure village halls host regular music events: | Due to proven benefit of music for those suffering from Dementia etc. | Across the Ward
DRAFT PLAN FOR REVIEW