## HAL AP
es
[5 empty] | CC | Community Councils in ward |  | CMcL | Craig McLachlan
[5 empty] | AM | Area Manager |  | JMcM | John McMillan
[5 empty] | AP | Area Partnership
[5 empty] | CLD | ELC Community Learning and Development
[5 empty] | CR | Community Reps from wider constituency
[5 empty] | HCDT | Community Development Trust
[5 empty] | HBA | Haddington Business Association
| ACTION PLAN | 2016 |  |  | HDCC | Haddington Community Council
| Last Reviewed | 2017-01-09
| by: | Sgibb
Status Code
| COMPLETED | Project complete |  |  | AP Budget 2016/17 | £100K | Amenity Services
| ACTIVE | Project in active progress or support mode |  |  |  | £50k | Roads
| DEVELOPMENT | Project in development / discussion phase |  |  |  | £50k | General
[6 empty] | £100K | Education
Town Centre & Local Economy
Champion: Karen Stevenson
Ref: | Goal/Aim What do we want for our ward? | What is needed? | How will this be achieved? | Where will this happen in our ward? | Lead/working with | Estimated Cost | Funding Source | Target End Date | Progress update
TC1 | Establish Haddington High Street as "The Best Town Square in Scotland" with a vibrant shopping centre. | Develop Action plan to drive improvements to Haddington Town Centre | Sub Group to be established with represenation from HCDT, HBA, HADAS, NHS, ELC | Haddington | AM / HCDT / HBA / HADAS / NHS / ELC
TC6 | Effectively Market all that Haddington & Lammermuir has to Offer | Improve signage to attractions | Through work of Town Centre Sub Group | Haddington | AM / HCDT / HBA / HADAS / NHS / ELC |  |  | 2016-03-31 | Fingerpoint signage in Haddington town centre painted.
TC2 | Establish Haddington High Street as "The Best Town Square in Scotland" with a vibrant shopping centre. | Property Audit | Establish locations of types of businesses and properties. | Haddington | AM / HCDT / HBA / HADAS / NHS / ELC
TC3 | Develop and Deliver a successful Access Strategy for Haddington Town Centre | More parking spaces and available bus parking spaces | Work with ELC and SusTRans | Haddington | AM/ ELC / HCDT | £30K | SusTrans |  | Phase 2 of project to produce a new design for the Town Centre is progressing and following a further award of funding from Sustrans ELC are in the process of tendering the architectural work package. The full invitation to tender will be issued during January 2017
TC4 | Make the Most of Haddington’s Assets including Buildings and Public Spaces | Promote attractions and assets. | Through work of Town Centre Sub Group | Haddington | AM / HCDT / HBA / HADAS / NHS / ELC
TC5 | Make the Most of Haddington’s Assets including Buildings and Public Spaces | Tourism asset audit to identify what’s there. | Through work of Town Centre Sub Group | Haddington | AM / HCDT / HBA / HADAS / NHS / ELC
Superfast Broadband
Champion: Cllr John McMillan
Ref: | Goal/Aim What do we want for our ward? | What is needed? | How will this be achieved? | Where will this happen in our ward? | Lead/working with | Estimated Cost | Funding Source | Target End Date | Progress update
SB1 | Superfast broadband established throughout the ward | Superfast broadband established throughout the ward | Work with Community Broadband Scotland (CBS)to establish mechanisms for delivering service to rural communities throughout the county. | Across the ward | AM/ELC/CBS |  |  |  | 29/11/16 CBS / ELC project on hold as extent / scope of any future East Lothian proejct will not be known until conclusion of Govt. R100 project in February 2018
Sustainable Travel
Champion: Nick Morgan
Ref: | Goal/Aim What do we want for our ward? | What is needed? | How will this be achieved? | Where will this happen in our ward? | Lead/working with | Estimated Cost | Funding Source | Target End Date | Progress update
ST1 | Increased use of active modes of travel (ie: walking and cycling) for trips within the Ward | Consultation on Local Priorities | Through East Lothian On the Move consultation | Across the ward | ELC Roads; AM; SusTrans, |  | Roads budget and match funding. £10K in total | 2016-03-31 | 10/12/15 Long List of Actions received from East Lothian On the Move consultation. To be considered by HAL AP
ST2 | Increased use of active modes of travel (ie: walking and cycling) for trips within the Ward | Install safe cycle storage in Haddington town centre | Install safe cycle storage facilities | Haddington | AM/ELC Roads | 9900 | Roads budget and match funding. £10K in total | 2016-01-31 | 31/03/16 Completed. Cycle stands installed
ST3 | Increased use of active modes of travel (ie: walking and cycling) for trips within the Ward | Ensure all paths have regular benches: | Through East Lothian On the Move consultation | Across the ward | AM/ELC Roads |  | Roads budget and match funding. £10K in total
ST4 | Public Transport provides the ward with reliable, accessible and regular services that meet the community’s needs | Improve community awareness of the services which are available: | By providing comprehensive public transport information in an easily digestible format such as a bus route map, and kept up to date. | Across the ward | AM/ELC
ST5 | Public Transport provides the ward with reliable, accessible and regular services that meet the community’s needs | Allow Garvald residents to use School Bus service to Haddington | Speak to ELC Transportation / Bus provider to explore options | Garvald | AP / ELC / Prentice Coaches |  |  |  | 21/12/15 ELC Transportation / Prentice Coaches advise not possible due to size of vehicle and DDA implications.
ST6 | Creative options are introduces for providing community transport solutions to areas where traditional forms of public transport are not viable. | Establish twice a week services to, Garvald & Morham, and Humbie & Blegbie | Speak to ELC Transportation / Bus provider to explore options | Garvald, Morham, Humbie and Blegbie | AP / ELC |  |  |  | 08/07/16 ELC are about to trial a community buse service in Humbie. Early idications is that this pilot may be extended to Garvald. More info to follow
ST7 | Children and young people can access appropriate facilities and services by sustainable means | Improve availability of safe active travel routes to school: | Establish areas of demand for shared-use paths to ensure young people have safe cycling and walking routes to access school and other facilities. | Across the Ward |  |  |  |  | New project - from C&YP sub group (prev CYP3)
ST8 | Increased use of active modes of travel (ie: walking and cycling) for trips within the Ward | Install safe cycle storage in villages and other locations around the Area | Install safe cycle storage facilities | Across the ward | AM/ELC Roads |  |  |  | 09/01/17 Proposals for location being considered by Gifford Community Council
Children and Young People
Champion: Penny Short
Ref: | Goal/Aim What do we want for our ward? | What is needed? | How will this be achieved? | Where will this happen in our ward? | Lead/working with | Estimated Cost | Funding Source | Target End Date | Progress update
CYP9 SCORE 26 | Young people in the ward have spaces to hang out and socialise, and access to high quality recreation facilities: | Develop leisure and sports activities | Work with Active Schools and children and young people etc. | Across the Ward
CYP2 SCORE 21 | Children and young people can access appropriate facilities and services by sustainable means | Regular Shuttle-Bus to Haddington for Young People living in villages / rural areas | Provide a regular (perhaps weekly/ fortnightly Fridays) Shuttle-Bus service to take young people into Haddington, and ensuring that attractions and activities are taking place at this time so that young people can play a more active role in their community. | Across the Ward
CYP8 SCORE 17 | Young people in the ward have spaces to hang out and socialise, and access to high quality recreation facilities: | Provide more places for young people to hang out in Haddington and rural communities | Work with young people to identify social spaces | Across the Ward |  |  |  |  | 09/01/17 Work underway to develop youth shelters in Garvald, Gifford and Haddington
CYP1 SCORE 16 | Children and Young People feel safe in their area: | Identifying unsafe areas and improving lighting in these areas | Establish areas and suggest improvements | Across the Ward |  |  |  |  | 11/07/16 Project moved to Safe and Vibrant Communities section - now CS10
CYP6 SCORE 15 | Children have opportunities to play and interact in safe and appropriate environments: | Encourage U-12s to make better use of the outdoor environment | Develop overseeing informal play sessions in outdoor spaces | Across the Ward
CYP3 SCORE 13 | Children and young people can access appropriate facilities and services by sustainable means | Improve availability of safe active travel routes to school: | Establish areas of demand for shared-use paths to ensure young people have safe cycling and walking routes to access school and other facilities. | Across the Ward |  |  |  |  | 06/07/16 Project moved to Sustainable Travel section- now ST7
CYP5 SCORE 13 | Children have opportunities to play and interact in safe and appropriate environments: | Improvements to the facilities at Neilson Park | Work with interested groups to identify requirements | Haddington |  |  |  |  | 06/07/16 Project moved to Inclusive Communities and Facilities section ICF9
CYP10 SCORE 11 | Young people have a positive, supported experience of education and are able to access guidance and options for their post-school choices. | Training for work schemes supporting local employers to take on young people in the area: | Work with local employers to establish and support internships for school leavers throughout the ward. | Across the Ward
CYP7 SCORE 5 | Young people in the ward have spaces to hang out and socialise, and access to high quality recreation facilities: | Homework Club for Young People | Establish homework clubs if required | Haddington
CYP11 | Children and Young People have opportunities to take part in arts, culture and media related events and activities | Children and Young People have opportunities to take part in arts, culture and media related events and activities |  | Haddington |  |  |  |  | 22/11/16 £19K Funding agreed by AP for Knox Academy Pipe Band
Health and Wellbeing
Champion: Gill Colston
Ref: | Goal/Aim What do we want for our ward? | What is needed? | How will this be achieved? | Where will this happen in our ward? | Lead/working with | Estimated Cost | Funding Source | Target End Date | Progress update
HW1 | The ward, and the county are served by an excellent East Lothian Community Hospital at the Roodlands site. | Sufficient Parking at the Hospital / Hospital site should tie in with Active and Public Transport where Possible / Ensure that high quality holistic care services should be rendered in partnership with key third sector agencies, eg: Macmillan Cancer Care, etc. | Work closely with NHS to influence the current and future parking resource / | Haddington | Gill Colston / Ann McCarthy / NHS Lothian |  |  |  | 22/11/16 Cllr John McMillan appointed as AP Championfor the new Community Hospital. Regular meetings scheduled with Miriam Anderson, Hospital Reprovision Team. Next meeting scheudled for 10/1/17
HW4 | There is improved awareness of mental health issues across the community and effective local services | Mental Health Sessions in School | Carry out mental health sessions in schools in a light hearted setting to introduce children to issues around mental health from an early age. | Across the Ward | ELC / NHS Lothian
HW5 | Older people are supported to live independently within their own community for as long as they choose | Identify and implement relevant support measures | Work with Older people and care providers to scope needs | Across the Ward | ELC / NHS Lothian
HW6 | Older people are supported to live independently within their own community for as long as they choose | Develop and support dementia friendly events across the Area | Work with dementia patients and care providers to scope needs | Across the Ward | ELC / NHS Lothian / Dementia Friendly East Lothian |  |  |  | 19/08/16 Meeting between Dementia Friendly East Lothian and Haddington Business Association to explore implementing DF business scheme. Tentative agremeent to proceed.
HW7 | People are enabled to live at home and access opportunities in their communities for as long as possible | Support the ELCCF Wellbeing passport pilot | Help find volunteers to act as interviewers needed to creat 400 passports during 16/17 | Across the Ward | East Lothian Community Care Forum (ELCCF)
Inclusive Communities and Facilities
Co-Champions: Rosemary Greenhill and Paul Darling
Ref: | Goal/Aim What do we want for our ward? | What is needed? | How will this be achieved? | Where will this happen in our ward? | Lead/working with | Estimated Cost | Funding Source | Target End Date | Progress update
ICF1 | Community based clubs, groups and individuals are able to access the facilities that exist within the ward easily and do so regularly. | Community Facilities Audit | Carry out audit of community facilities throughout the ward assessing all facilities for – capacity; current use; opening hours; booking procedure; location | Across the Ward |  |  |  |  | 05/07/16 - PD to amend audit questionnaire and to pass to SG for circulation to community council reps for completion
ICF2 | Community based clubs, groups and individuals are able to access the facilities that exist within the ward easily and do so regularly. | Promotion of local facilities and the activities on offer | Through Directory/ What’s On Guide, etc. | Across the Ward |  |  |  |  | 09/01/17 Whats On East Lothian database launched
ICF3 | All areas of the ward are equipped with the facilities required to support thriving local communities. | Skate Park in Haddington | Work with HDCC to deliver skatepark project | Haddington | AM / HDCC / ELC | 108000 | Various | 2016-06-01 | 03/06/16 Complete
ICF4 | All areas of the ward are equipped with the facilities required to support thriving local communities. | Athelstaneford Skatepark: | Majority of funding secured from Viridor, need small amount of additional funding to see project through to completion. | Athelstaneford | Athelstaneford Parent Council |  | Most of funding secured from Viridor. HAL AP agreed to fund £2,297 on 24/6/15 | 2015-12-31 | 03/06/16 Complete
ICF5 | All areas of the ward are equipped with the facilities required to support thriving local communities. | Utilize Empty Accommodation/ Halls: | Better coordination on how community facilities can be booked: | Across the Ward
ICF6 | All areas of the ward are equipped with the facilities required to support thriving local communities. | Improve the park space at the Nungate | Investigate options to encourage wider use | Haddington
ICF7 | All areas of the ward are equipped with the facilities required to support thriving local communities. | Assess need for additional facilities in villages. |  | Across the Ward | Regional CCs, Area Partnership, Local Young Peoples
ICF8 | All areas of the ward are equipped with the facilities required to support thriving local communities. | Secure a sustainable future for village and other community halls as a key community facility. | Support the local community | Across the Ward | ELC
ICF9 | Children have opportunities to play and interact in safe and appropriate environments: | Improvements to the facilities at Neilson Park | Work with interested groups to identify requirements | Haddington |  |  |  |  | 06/07/16HAL AP to have representation on Friends of Neilson Park group.
ICF10 | All areas of the ward are equipped with the facilities required to support thriving local communities. | Improvements to Amisfield Walled Garden | Work with Amisfield Preservation Trust | Haddington |  |  |  |  | 23/01/16 HAL AP approved £5064.38 as CTP to release Viridor Credit funding for new community education building
ICF11 | Local Assets are protected and enhanced | Restore the banking of the Papana river in Garvald | Install gabion baskets | Garvald | AM / ELC Amenity Services | 5775 | AP Amenity Services budget 16/17 | End June 16 | 01/10/16 Project to install gabion baskets on the Papana River bank complete
ICF12 | The negative impact of high school catchment boundaries on community cohesion is overcome. | Make representations to the School Catchment Review consultation: Taking place as part of the MIR. |  | Across the Ward
Safe and Vibrant Communities
Champion: Paul Sales
Ref: | Goal/Aim What do we want for our ward? | What is needed? | How will this be achieved? | Where will this happen in our ward? | Lead/working with | Estimated Cost | Funding Source | Target End Date | Progress update
SVC9 | Improved road and pedestrian safety throughout the ward | Speed reduction measures on Whittingehame Drive at the entrance to the football pitches / skatepark | Install speed table with red block paving effect oout early 2016 as agreed with P Forsyth. | Whittingehame Drive, Haddington | ELC Roads | 35000 | Roads | 2016-03-31 | 30/05/16 Completed
SVC1 | Improved road and pedestrian safety throughout the ward | A permanent Speed Reactive Sign in East Saltoun | Work with ELC Roads Team to identify solution. | East Saltoun | ELC Roads | 5000 | Roads | 2015-10-31 | 22/12/15 HAL AP agreed funding on 24/6/15. Sign installed and operational October 2015
SVC2 | Improved road and pedestrian safety throughout the ward | Effective traffic calming measures in Bolton to address the increase in traffic in the area | Work with ELC Roads Team to identify solution. | Bolton | ELC Roads |  |  |  | 04/08/16 HAL AP agreed to fund £3750 to install new speed reactive sign and additional NAL socket
SVC3 | Improved road and pedestrian safety throughout the ward | Effective traffic calming measures in Humbie to address the increase in traffic in the area | Work with ELC Roads Team to identify solution. | Humbie | ELC Roads
SVC4 | Enhanced Community Policing throughout the ward | Focus on prevention rather than reaction. | Integrate the priorities of the Police Scotland ward plan into the Area Plan | Across the Ward | Police Scotland
SVC5 | Flood prevention along watercourses is improved. | Improve flood prevention measures at the riverside between Tyne Court and Bridge Street. | Work with ELC Roads Team to identify solution. | Haddington | ELC Roads
SVC6 | Reduced incidences of anti-social behaviour in the ward | Proactive multi-agency targetting of Young People to educate and reduce incidences of potential ASB | Communicate with Young People | Across the Ward | ELC | 475 | General | 2016-03-31 | 30/06/16 Completed
SVC7 | Reduced incidences of substance misuse in the ward | Proactive multi-agency targetting of Young People to educate and reduce incidences of potential ASB | Communicate with Young People | Across the Ward | ELC | 475 | General | 2016-03-31 | 30/06/16 Completed
SVC8 | People feel safe and secure in their own homes |  |  | Across the Ward
SVC10 | Children and Young People feel safe in their area: | Identifying unsafe areas and improving lighting in these areas | Establish areas and suggest improvements | Across the Ward |  |  |  |  | 11/07/16 Project moved from Children and Young People section - previously CYP1
SVC11 | Improve Community resilience and contingency | Encourage and support Communities to develop and implement resilience plans for their local area |  | Across the Ward
DRAFT PLAN FOR REVIEW

## C&YP wishlist
[5 empty] | CC | Community Councils in ward |  | CMcL | Craig McLachlan
[5 empty] | AM | Area Manager |  | JMcM | John McMillan
[5 empty] | AP | Area Partnership
[5 empty] | CLD | ELC Community Learning and Development
[5 empty] | CR | Community Reps from wider constituency
[5 empty] | HCDT | Community Development Trust
[5 empty] | HBA | Haddington Business Association
| ACTION PLAN | 2016 |  |  | HDCC | Haddington Community Council
| Last Reviewed | 2016-05-20
| by: | Doug Haig & Nettie Sadler - Post 1st Young People's Group Meeting Held 19.05.16
Status Code
| COMPLETED | Project complete
| ACTIVE | Project in active progress or support mode
| DEVELOPMENT | Project in development / discussion phase
Children and Young People
Champion: Penny Short
Ref: | Goal/Aim What do we want for our ward? | What is needed? | How will this be achieved? | Where will this happen in our ward? | Lead/working with | Estimated Cost | Funding Source | Target End Date | Progress update
Mental Health Support for Young People.
Mental Health Issues linked to all other plans.
Support for mental health issues. Confidence, body image, self esteem.
More inclusion for children/young people with disabilities, mental health issues etc.
Thinking about small issues such as LAC/Disability groups that may not come up.
Social & recreational opportunities for children with additional support needs
Flood Light / Grass area at Knox (or Millfield) for Winter Training Use by All Schools & Community Groups.
FloodLit areas of Millfield & Knox playing fields.
More outdoor fitness / multi gym areas.
Shared use paths to encourage safe walking, running, cycling. Envisaging a Glentress like mapped facility. Colour coded routes. Tie in sport clubs and historical sights.
Forest School / Nature play and nurture
Develop projects for Early Years / Children.
Support for Parents with Early Learning
Engage with Primary school age children in consultation, e.g. through pupil councils.
Ensure all areas in Ward, including outside Knox catchment are involved.
Areas where youths can interact with adults to improve social skills.
Rewards for attainment/endeavours outwith school e.g. Duke of Edinburgh Etc.
School Attendance
Sexual Health Education / Internet Safety
Internet Safety
Lease hire/purchase of minibus. Access of this bus could be made available to schools, community groups, rural groups. This has to work in conjunction with training for drivers etc.
DRAFT PLAN FOR REVIEW