## Table 1 - AHSP Years 1-5
MORE HOMES DIVISION
STRATEGIC HOUSING INVESTMENT PLAN 2026/27-2030/31
APPENDIX B Table 1 - AFFORDABLE HOUSING SUPPLY PROGRAMME - Years 1-5 2026/27-2030/31
| LOCAL AUTHORITY: | EAST LOTHIAN COUNCIL
HARP Number | PROJECT | SUB-AREA | PRIORITY | GEOGRAPHIC CODE (Numeric Value - from Drop Down Table Below) | RSL | Developer | UNITS - TENURE | [6 empty] | UNITS - BUILT FORM |  |  |  | UNITS - TYPE |  |  |  | GREENER STANDARDS | APPROVAL DATE | UNITS SITE STARTS | [5 empty] | UNITS - COMPLETIONS | [5 empty] | SG AHSP FUNDING REQUIREMENT (£0.000M)
[7 empty] | Social Rent | Mid Market Rent | LCHO - Shared Equity | LCHO - Shared Ownership | LCHO - Improvement for Sale | PSR | Total Units | Rehab | Off the Shelf | NB | Total Units | GN | Specialist Provision | Type of Specialist | Total Units by Type | Enter Y or N | Financial Year (Estimated or Actual) | 26/27 | 27/28 | 28/29 | 29/30 | 30/31 | TOTAL | 26/27 | 27/28 | 28/29 | 29/30 | 30/31 | TOTAL | 26/27 | 27/28 | 28/29 | 29/30 | 30/31 | TOTAL
T36754 | Bayswell Road ph 2 | Dunbar | Medium | 6 | ELHA |  | 27 | [5 empty] | 27 |  |  | 27 | 27 | 27 |  |  | 27 | Y | 28/29 |  |  |  | 27 |  | 27 |  |  |  | 27 |  | 27 |  |  | 2.765 | 0.691 |  | 3.456
P44897 | Blindwells area5 ph1 | Blindwells | High | 9 | ELHA | Persimmon | 52 | [5 empty] | 52 |  |  | 52 | 52 | 46 | 6 | mix | 52 | Y | 25/26 | [5 empty] | 0 |  | 52 |  |  |  | 52 | 5.152 |  |  |  |  | 5.152
P46447 | Blindwells area5 ph2 | Blindwells | High | 9 | CRE | Avant | 37 | [5 empty] | 37 |  |  | 37 | 37 | 31 | 6 | mix | 37 | Y | 28/29 |  |  | 37 |  |  | 37 |  |  |  | 37 |  | 37 |  |  | 3.688 | 0.921 |  | 4.609
P46446 | Blindwells area5 ph2 | Blindwells | High | 8 | CRE | Avant |  | 14 |  |  |  |  | 14 |  |  | 14 | 14 | 14 |  |  | 14 | Y | 28/29 |  |  | 14 |  |  | 14 |  |  |  | 14 |  | 14 |  |  | 1.104 | 0.276 |  | 1.38
P47385 | Blindwells Town Centre | Blindwells | High | 8 | PfP | PfP |  | 65 |  |  |  |  | 65 |  |  | 65 | 65 | 50 | 15 | elderly | 65 | Y | 28/29 |  |  | 65 |  |  | 65 |  |  |  | 65 |  | 65 |  | 0.78 | 2.475 | 2.476 |  | 5.731
P47382 | Blindwells area 4a | Blindwells | High | 8 | PfP |  | 42 | [5 empty] | 42 |  |  | 42 | 42 | 40 | 2 | wh/chair | 42 | Y | 24/25 | [5 empty] | 0 |  | 42 |  |  |  | 42 | 0.885 |  |  |  |  | 0.885 | Possible chariatable bond
P41846 | Blindwells area 6 ph 1 | Blindwells | Medium | 8 | ELC | Bellway | 23 | [5 empty] | 23 |  |  | 23 | 23 | 17 | 6 | mix | 23 | Y | 26/27 | 23 |  |  |  |  | 23 |  | 23 |  |  |  | 23 | 1.219 | 1.219 |  |  |  | 2.438
P41517 | Blindwells 6 ph 2 | Blindwells | Medium | 8 | ELC | Bellway | 42 | [5 empty] | 42 |  |  | 42 | 42 | 42 |  | mix | 42 | Y | 27/28 |  | 42 |  |  |  | 42 |  |  | 42 |  |  | 42 |  | 2.226 | 2.226 |  |  | 4.452
P48595 | Blindwells 7 | Blindwells | Medium | 8 | ELC | Cala | 37 | [5 empty] | 37 |  |  | 37 | 37 | 37 |  |  | 37 | Y | 29/30 |  |  |  | 37 |  | 37 |  |  |  |  | 37 | 37 |  |  |  | 1.961 | 1.961 | 3.922
P46463 | Blindwells area 9 | Blindwells | Medium | 8 | Hillcrest | Taylor Wimpey | 53 | [5 empty] | 53 |  |  | 53 | 53 | 48 | 5 | mix | 53 | Y | 30/31 |  |  |  |  | 53 | 53 | [5 empty] | 0 |  |  |  |  | 2.809 | 2.809
| Blindwells area 10 | Blindwells | Medium | 8 | ELC | unallocated | 2 | [5 empty] | 2 |  |  | 2 | 2 | 2 |  |  | 2 | Y | 29/30 |  |  |  |  | 2 | 2 |  |  |  |  | 2 | 2 |  |  |  |  | 0.18 | 0.18
P45492 | Brown Street | Haddington | Low | 8 | ELC |  | 9 | [5 empty] | 9 |  |  | 9 | 9 | 8 | 1 | Amb | 9 | Y | 29/30 |  |  |  |  | 9 | 9 | [5 empty] | 0 |  |  |  |  | 0.9 | 0.9
P46480 | Craighall - Oldcraighall Ph 1 | Musselburgh | Medium | 9 | ELC | Persimmon | 38 | [5 empty] | 38 |  |  | 38 | 38 | 34 | 4 | Mix | 38 | Y | 29/30 |  |  |  | 38 |  | 38 |  |  |  |  | 38 | 38 |  |  |  | 4 |  | 4
P46481 | Craighall - Oldcraighall Ph 2 | Musselburgh | Medium | 9 | ELC | Persimmon | 37 | [5 empty] | 37 |  |  | 37 | 37 | 34 | 3 | Mix | 37 | Y | 30/31 |  |  |  |  | 37 | 37 | [5 empty] | 0 |  |  |  |  | 4 | 4
P46458 | Craighall - Whitehill Ph 1 (SR) | Musselburgh | Medium | 9 | WHE | Persimmon | 19 | [5 empty] | 19 |  |  | 19 | 19 | 15 | 4 | Mix | 19 | Y | 29/30 |  |  |  | 19 |  | 19 |  |  |  |  | 19 | 19 |  |  |  |  | 3.433 | 3.433
P46457 | Craighall - Whitehill Ph 1 (MMR) | Musselburgh | Medium | 9 | WHE | Persimmon |  | 20 |  |  |  |  | 20 |  |  | 20 | 20 | 20 | 0 | Mix | 20 | Y | 29/30 |  |  |  | 20 |  | 20 |  |  |  |  | 20 | 20 |  |  |  |  | 1.4 | 1.4
P46886 | Courier Building 2 | Haddington | Medium | 5 | ELHA |  | 11 | [5 empty] | 11 |  |  | 11 | 11 | 11 |  |  | 11 | Y | 29/30 |  |  |  | 11 |  | 11 |  |  |  |  | 11 | 11 |  |  |  | 1.056 | 0.352 | 1.408
P46462 | Church Street | Tranent | High | 10 | Hillcrest | Private | 17 | [5 empty] | 17 |  |  | 17 | 17 | 17 |  |  | 17 | Y | 28/29 |  |  | 17 |  |  | 17 |  |  |  | 17 |  | 17 |  |  |  | 0.54 |  | 0.54
P43275 | Church Street | Tranent | High | 10 | Hillcrest | Private |  | 11 |  |  |  |  | 11 |  |  | 11 | 11 | 11 |  |  | 11 | Y | 28/29 |  |  | 11 |  |  | 11 |  |  |  | 11 |  | 11 |  |  |  | 0.84 |  | 0.84
P46455 | Dolphinstone Ph4 | Wallyford | High | 9 | WHE | Taylor Wimpey | 62 | [5 empty] | 62 |  |  | 62 | 62 | 58 | 4 | wh/chair | 62 | Y | 27/28 |  | 62 |  |  |  | 62 |  |  | 30 | 32 |  | 62 |  |  | 3.286 | 3.286 |  | 6.572
P44905 | Dolphinstone Ph 2B | Wallyford | Medium | 9 | ELC | Taylor Wimpey | 60 | [5 empty] | 60 |  |  | 60 | 60 | 54 | 6 | wh/chair | 60 | Y | 28/29 |  |  | 30 | 30 |  | 60 |  |  |  | 30 | 30 | 60 |  |  |  | 3.18 | 3.18 | 6.36
P45536 | Dolphinstone Ph 2C | Wallyford | Medium | 9 | ELC | Taylor Wimpey | 65 | [5 empty] | 65 |  |  | 65 | 65 | 59 | 6 | mix | 65 | Y | 29/30 |  |  |  | 35 | 30 | 65 |  |  |  |  | 35 | 35 |  |  |  |  | 1.855 | 1.855
P41590 | Elphinstone West Phase 2 | Elphinstone | High | 5 | ELHA | Bellway | 28 | [5 empty] | 28 |  |  | 28 | 28 | 28 |  |  | 28 | Y | 25/26 | [5 empty] | 0 |  | 28 |  |  |  | 28 | 1.755 |  |  |  |  | 1.755
P42753 | Herdmanflat 1 | Haddington | High | 9 | ELC | Cruden | 51 | [5 empty] | 51 |  |  | 51 | 51 |  | 51 | Older People | 51 | Y | 25/26 | [5 empty] | 0 |  | 51 |  |  |  | 51 |  | 2.783 |  |  |  | 2.783
P42091 | Herdmanflat 1A | Haddington | High | 9 | ELC | Cruden | 57 | [5 empty] | 57 |  |  | 57 | 57 |  | 57 | Older People | 57 | Y | 27/28 |  | 57 |  |  |  | 57 |  |  |  | 57 |  | 57 |  |  | 3 | 3 |  | 6
P43445 | Herdmanflat 2 | Haddington | Medium | 9 | ELC | Cruden | 37 | [5 empty] | 37 | 37 |  |  | 37 |  | 37 | Older People | 37 | Y | 28/29 |  |  | 37 |  |  | 37 |  |  |  |  | 37 | 37 |  |  |  | 1.5 | 0.256 | 1.756
P46459 | Letham (site 6) | Haddington | Medium | 8 | WHE | Taylor Wimpey | 22 | [5 empty] | 22 |  |  | 22 | 22 | 21 | 1 | amb | 22 | Y | 25/26 | [5 empty] | 0 | 22 |  |  |  |  | 22 | [5 empty] | 0
P46454 | Letham (site 6) | Haddington | Medium | 7 | WHE | Taylor Wimpey |  | 12 |  |  |  |  | 12 |  |  | 12 | 12 | 12 | 0 |  | 12 | Y | 25/26 | [5 empty] | 0 | 12 |  |  |  |  | 12 | [5 empty] | 0
P41575 | Letham M&M Ph 3 | Haddington | Medium | 5 | PfP | Springfield | 15 | [5 empty] | 15 |  |  | 15 | 15 | 13 | 2 | amb | 15 | Y | 26/27 | 15 |  |  |  |  | 15 |  | 15 |  |  |  | 15 | 1.92 |  |  |  |  | 1.92
P44879 | Mall Avenue | Musselburgh | High | 9 | WHE | Dundas |  | 11 |  |  |  |  | 11 |  |  | 11 | 11 | 8 | 3 | Ambulant | 11 | Y | 27/28 |  | 11 |  |  |  | 11 |  |  | 11 |  |  | 11 |  | 0.9 |  |  |  | 0.9
P46551 | Mansfield Road | Musselburgh | Low | 9 | ELC |  | 10 | [5 empty] | 10 |  |  | 10 | 10 | 10 |  |  | 10 | Y | 29/30 |  |  |  |  | 10 | 10 |  |  |  |  | 10 | 10 |  |  |  | 0.2 | 0.2 | 0.4
P47168 | Schaw Road | Prestonpans | Low | 9 | ELC |  | 2 | [5 empty] | 2 |  |  | 2 | 2 | 2 |  |  | 2 | Y | 27/28 | 2 |  |  |  |  | 2 |  | 2 |  |  |  | 2 |  | 0.2 |  |  |  | 0.2
P45496 | Tranent site | Tranent | Medium | 8 | ELC |  | 25 | [5 empty] | 25 |  |  | 25 | 25 | 21 | 4 | Ame | 25 | Y | 29/30 |  |  |  | 25 |  | 25 |  |  |  |  | 25 | 25 |  |  |  | 1 | 1.75 | 2.75
P41512 | Wallyford - Area 1 ph 1 | Wallyford | High | 8 | ELC |  | 36 | [5 empty] | 36 |  |  | 36 | 36 | 30 | 6 | Mix | 36 | Y | 26/27 | 36 |  |  |  |  | 36 |  | 36 |  |  |  | 36 | 1.1 | 1.326 |  |  |  | 2.426
P41699 | Wallyford - Area 1 ph 2 (SR) | Wallyford | High | 8 | ELC |  | 16 | [5 empty] | 16 |  |  | 16 | 16 | 12 | 4 | Mix | 16 | Y | 28/29 |  |  | 16 |  |  | 16 |  |  |  | 16 |  | 16 |  |  | 1.68 |  |  | 1.68
P41705 | Wallyford - Area 1 ph 2 (MMR) | Wallyford | High | 8 | ELC |  |  | 24 |  |  |  |  | 24 |  |  | 24 | 24 | 24 | 0 | Mix | 24 | Y | 28/29 |  |  | 24 |  |  | 24 |  |  |  | 24 |  | 24 |  |  | 1.68 |  |  | 1.68
P45493 | Wallyford - Area 5a | Wallyford | High | 9 | WHE | McTaggart | 29 | [5 empty] | 29 |  |  | 29 | 29 |  | 29 | Older People | 29 | Y | 21/22 | [5 empty] | 0 | 29 |  |  |  |  | 29 | [5 empty] | 0
P45494 | Wallyford - Area 5b | Wallyford | High | 9 | WHE | McTaggart |  | 61 |  |  |  |  | 61 |  |  | 61 | 61 |  | 61 |  | 61 | Y | 21/22 | [5 empty] | 0 | 61 |  |  |  |  | 61 | [5 empty] | 0
P46460 | Wallyford - Area 6a (SR) | Wallyford | Medium | 9 | WHE | McTaggart | 19 | [5 empty] | 19 |  |  | 19 | 19 | 17 | 2 | wh/chair | 19 | Y | 26/27 | 19 |  |  |  |  | 19 |  | 19 |  |  |  | 19 | 2.28 |  |  |  |  | 2.28
P43714 | Wallyford - Area 6a (MMR) | Wallyford | Medium | 9 | WHE | McTaggart |  | 9 |  |  |  |  | 9 |  |  | 9 | 9 | 9 | 0 |  | 9 | Y | 26/27 | 9 |  |  |  |  | 9 |  | 9 |  |  |  | 9 | 0.754 |  |  |  |  | 0.754
P41588 | Wallyford - Area 6b | Wallyford | Medium | 9 | WHE | McTaggart | 32 | [5 empty] | 32 |  |  | 32 | 32 | 30 | 2 | wh/chair | 32 | Y | 27/28 |  | 32 |  |  |  | 32 |  |  | 32 |  |  | 32 |  | 3.835 |  |  |  | 3.835
P45740 | Wallyford Primary School | Wallyford | High | 9 | ELC |  | 60 | [5 empty] | 60 |  |  | 60 | 60 | 54 | 6 | wh/chair | 60 | Y | 26/27 | 60 |  |  |  |  | 60 | 30 | 30 |  |  |  | 60 | 1.648 | 1 |  |  |  | 2.648
P46465 | Whitecraig South (SR) | Whitecraig | Low | 9 | Hillcrest | Bellway | 20 | [5 empty] | 20 |  |  | 20 | 20 | 16 | 4 | wh/chair | 20 | Y | 27/28 |  | 20 |  |  |  | 20 |  | 20 |  |  |  | 20 |  | 2 |  |  |  | 2
P46464 | Whitecraig South (MMR) | Whitecraig | Low | 9 | Hillcrest | Bellway |  | 20 |  |  |  |  | 20 |  |  | 20 | 20 | 20 | 0 |  | 20 | Y | 27/28 |  | 20 |  |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 1.6 |  |  | 1.6
P42068 | Whitecraig South ph 2 | Whitecraig | Low | 9 | ELC | Bellway | 53 | [5 empty] | 53 |  |  | 53 | 53 | 47 | 6 | Ambulant Disabled W/ch | 53 | Y | 27/28 |  | 53 |  |  |  | 53 |  |  | 20 | 33 |  | 53 |  |  | 3 | 2.5 |  | 5.5
P47428 | Windygoul South Ph2 | Tranent | Medium | 6 | CRE | Springfield | 32 | [5 empty] | 32 |  |  | 32 | 32 | 26 | 6 | amb | 32 | Y | 27/28 |  | 32 |  |  |  | 32 |  |  | 32 |  |  | 32 |  | 4.097 |  |  |  | 4.097
P41595 | Windygoul South Ph3 | Tranent | Medium | 8 | ELHA | Springfield | 50 | [5 empty] | 50 |  |  | 50 | 50 | 36 | 14 | Mix | 50 | Y | 28/29 |  |  | 50 |  |  | 50 |  |  |  |  | 50 | 50 |  |  | 4.704 | 3.136 |  | 7.84
| OMPs |  | High | 10 | ELC |  | 20 | [5 empty] | 20 |  | 20 |  | 20 | 20 |  |  | 20 | N |  | 4 | 4 | 4 | 4 | 4 | 20 | 4 | 4 | 4 | 4 | 4 | 20 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 2
| Total | [5 empty] | 1247 | 247 | 0 | 0 | 0 | 0 | 1494 | 37 | 20 | 1437 | 1494 | 1131 | 363 |  | 1494 |  |  | 168 | 333 | 305 | 246 | 145 | 1197 | 158 | 331 | 191 | 367 | 318 | 1365 | 17.113 | 20.766 | 31.608 | 30.963 | 22.676 | 123.126
Drop Down Table Values
[22 empty] | Numerical Value | Geographic Code |  |  |  |  | RSL - SR - Greener
[22 empty] | 1 | West Highland/Island Authorities/Remote/Rural Argyll -RSL - SR - Greener |  |  |  |  | RSL - SR - Other
[22 empty] | 2 | West Highland/Island Authorities/Remote/Rural Argyll |  |  |  |  | RSL - SR - Greener
[22 empty] | 3 | Other Rural |  |  |  |  | RSL - SR - Other
[22 empty] | 4 | Other Rural |  |  |  |  | RSL - SR - Greener
[22 empty] | 5 | City and Urban |  |  |  |  | RSL - SR - Other
[22 empty] | 6 | City and Urban |  |  |  |  | RSL - Mid-Market Rent - Greener
[22 empty] | 7 | All |  |  |  |  | RSL - Mid-Market Rent - Other
[22 empty] | 8 | All |  |  |  |  | Council - SR - Greener
[22 empty] | 9 | All |  |  |  |  | Council -SR - Other
[22 empty] | 10 | All

## Table 1B - Deliverable AHSP
HARP Number | PROJECT | SUB-AREA | PRIORITY | GEOGRAPHIC CODE (Numeric Value - from Drop Down Table Below) | RSL | DEVELOPER | UNITS - TENURE | [6 empty] | UNITS - BUILT FORM |  |  |  | UNITS - TYPE |  |  |  | GREENER STANDARDS | APPROVAL DATE | UNITS SITE STARTS | [5 empty] | UNITS - COMPLETIONS | [5 empty] | SG AHSP FUNDING REQUIREMENT (£0.000M)
[7 empty] | Social Rent | Mid Market Rent | LCHO - Shared Equity | LCHO - Shared Ownership | LCHO - Improvement for Sale | PSR | Total | Rehab | Off the Shelf | NB | Total | GN | Specialist Provision | Type of Specialist | Total | Enter Y or N | Financial Year (Estimated or Actual) | 26/27 | 27/28 | 28/29 | 29/30 | 30/31 | TOTAL | 26/27 | 27/28 | 28/29 | 29/30 | 30/31 | TOTAL | 26/27 | 27/28 | 28/29 | 29/30 | 30/31 | TOTAL
T36754 | Bayswell Road ph 2 | Dunbar | Medium | 6 | ELHA |  | 27 |  |  |  | 27 |  | 27 |  |  | 27 | 27 | 27 |  |  | 27 | Y | 28/29 |  |  |  | 27 |  | 27 |  |  |  | 27 |  | 27 |  |  | 2.765 | 0.691 |  | 3.456
P47385 | Blindwells Town Centre | Blindwells | High | 8 | PfP | PfP | 65 |  |  |  |  | 65 | 65 |  |  | 65 | 65 | 50 | 15 | elderly | 65 | Y | 28/29 |  |  | 65 |  |  | 65 |  |  |  | 65 |  | 65 |  | 0.78 | 2.475 | 2.476 |  | 5.731
P47382 | Blindwells area 4a | Blindwells | High | 8 | PfP |  | 42 | [5 empty] | 42 |  |  | 42 | 42 | 40 | 2 | wh/chair | 42 | Y | 24/25 | [5 empty] | 0 |  | 42 |  |  |  | 42 | 0.885 |  |  |  |  | 0.885 | Possible chariatable bond
P44897 | Blindwells area5 ph1 | Blindwells | High | 9 | ELHA | Persimmon | 52 | [5 empty] | 52 |  |  | 52 | 52 | 46 | 6 | mix | 52 | Y | 25/26 | [5 empty] | 0 |  | 52 |  |  |  | 52 | 5.152 |  |  |  |  | 5.152
P46447 | Blindwells area5 ph2 | Blindwells | High | 9 | CRE | Avant | 37 | [5 empty] | 37 |  |  | 37 | 37 | 31 | 6 | mix | 37 | Y | 28/29 |  |  | 37 |  |  | 37 |  |  |  | 37 |  | 37 |  |  | 3.688 | 0.921 |  | 4.609
P46446 | Blindwells area5 ph2 | Blindwells | HIgh | 8 | CRE | Avant |  | 14 |  |  |  |  | 14 |  |  | 14 | 14 | 14 |  |  | 14 | Y | 28/29 |  |  | 14 |  |  | 14 |  |  |  | 14 |  | 14 |  |  | 1.104 | 0.276 |  | 1.38
P41846 | Blindwells area 6 ph 1 | Blindwells | Medium | 8 | ELC | Bellway | 23 | [5 empty] | 23 |  |  | 23 | 23 | 17 | 6 | mix | 23 | Y | 26/27 | 23 |  |  |  |  | 23 |  | 23 |  |  |  | 23 | 1.219 | 1.219 |  |  |  | 2.438
P41517 | Blindwells 6 ph 2 | Blindwells | Medium | 8 | ELC | Bellway | 42 | [5 empty] | 42 |  |  | 42 | 42 | 42 |  | mix | 42 | Y | 27/28 |  | 42 |  |  |  | 42 |  |  | 42 |  |  | 42 |  | 2.226 | 2.226 |  |  | 4.452
P48595 | Blindwells 7 | Blindwells | Medium | 8 | ELC | Cala | 37 | [5 empty] | 37 |  |  | 37 | 37 | 37 |  |  | 37 | Y | 29/30 |  |  |  | 37 |  | 37 |  |  |  |  | 37 | 37 |  |  |  | 1.961 | 1.961 | 3.922
P46463 | Blindwells area 9 | Blindwells | Medium | 8 | Hillcrest | Taylor Wimpey | 53 | [5 empty] | 53 |  |  | 53 | 53 | 48 | 5 | mix | 53 | Y | 30/31 |  |  |  |  | 53 | 53 | [5 empty] | 0 |  |  |  |  | 2.809 | 2.809
| Blindwells area 10 | Blindwells | Medium | 8 | ELC | unallocated | 2 | [5 empty] | 2 |  |  | 2 | 2 | 2 |  |  | 2 | Y | 29/30 |  |  |  |  | 2 | 2 |  |  |  |  | 2 | 2 |  |  |  |  | 0.18 | 0.18
P46480 | Craighall - Oldcraighall Ph 1 | Musselburgh | Medium | 9 | ELC | Persimmon | 38 | [5 empty] | 38 |  |  | 38 | 38 | 34 | 4 | Mix | 38 | Y | 29/30 |  |  |  | 38 |  | 38 |  |  |  |  | 38 | 38 |  |  |  | 4 |  | 4
P46481 | Craighall - Oldcraighall Ph 2 | Musselburgh | Medium | 9 | ELC | Persimmon | 37 | [5 empty] | 37 |  |  | 37 | 37 | 34 | 3 | Mix | 37 | Y | 30/31 |  |  |  |  | 37 | 37 | [5 empty] | 0 |  |  |  |  | 4 | 4
P46458 | Craighall - Whitehill Ph 1 (SR) | Musselburgh | Medium | 9 | WHE | Persimmon | 19 | [5 empty] | 19 |  |  | 19 | 19 | 15 | 4 | Mix | 19 | Y | 29/30 |  |  |  | 19 |  | 19 |  |  |  |  | 19 | 19 |  |  |  |  | 3.433 | 3.433
P46457 | Craighall - Whitehill Ph 1 (MMR) | Musselburgh | Medium | 9 | WHE | Persimmon |  | 20 |  |  |  |  | 20 |  |  | 20 | 20 | 20 | 0 | Mix | 20 | Y | 29/30 |  |  |  | 20 |  | 20 |  |  |  |  | 20 | 20 |  |  |  |  | 1.4 | 1.4
P46462 | Church Street | Tranent | High | 10 | Hillcrest | Private | 17 | [5 empty] | 17 |  |  | 17 | 17 | 17 |  |  | 17 | Y | 28/29 |  |  | 17 |  |  | 17 |  |  |  | 17 |  | 17 |  |  |  | 0.54 |  | 0.54
P43275 | Church Street | Tranent | High | 10 | Hillcrest | Private |  | 11 |  |  |  |  | 11 |  |  | 11 | 11 | 11 |  |  | 11 | Y | 28/29 |  |  | 11 |  |  | 11 |  |  |  | 11 |  | 11 |  |  |  | 0.84 |  | 0.84
P46455 | Dolphinstone Ph4 | Wallyford | High | 9 | WHE | Taylor Wimpey | 62 | [5 empty] | 62 |  |  | 62 | 62 | 58 | 4 | wh/chair | 62 | Y | 27/28 |  | 62 |  |  |  | 62 |  |  | 30 | 32 |  | 62 |  |  | 3.286 | 3.286 |  | 6.572
P44905 | Dolphinstone Ph 2B | Wallyford | Medium | 9 | ELC | Taylor Wimpey | 60 | [5 empty] | 60 |  |  | 60 | 60 | 54 | 6 | wh/chair | 60 | Y | 28/29 |  |  | 30 | 30 |  | 60 |  |  |  | 30 | 30 | 60 |  |  |  | 3.18 | 3.18 | 6.36
P45536 | Dolphinstone Ph 2C | Wallyford | Medium | 9 | ELC | Taylor Wimpey | 65 | [5 empty] | 65 |  |  | 65 | 65 | 59 | 6 | mix | 65 | Y | 29/30 |  |  |  | 35 | 30 | 65 |  |  |  |  | 35 | 35 |  |  |  |  | 1.855 | 1.855
P41590 | Elphinstone West Phase 2 | Elphinstone | High | 5 | ELHA | Bellway | 28 | [5 empty] | 28 |  |  | 28 | 28 | 28 |  |  | 28 | Y | 25/26 | [5 empty] | 0 |  | 28 |  |  |  | 28 | 1.755 |  |  |  |  | 1.755
P42753 | Herdmanflat 1 | Haddington | High | 9 | ELC | Cruden | 51 | [5 empty] | 51 |  |  | 51 | 51 |  | 51 | Older People | 51 | Y | 25/26 | [5 empty] | 0 |  | 51 |  |  |  | 51 |  | 2.783 |  |  |  | 2.783
P42091 | Herdmanflat 1A | Haddington | High | 9 | ELC | Cruden | 57 | [5 empty] | 57 |  |  | 57 | 57 |  | 57 | Older People | 57 | Y | 27/28 |  | 57 |  |  |  | 57 |  |  |  | 57 |  | 57 |  |  | 3 | 3 |  | 6
P43445 | Herdmanflat 2 | Haddington | Medium | 9 | ELC | Cruden | 37 | [5 empty] | 37 | 37 |  |  | 37 |  | 37 | Older People | 37 | Y | 28/29 |  |  | 37 |  |  | 37 |  |  |  |  | 37 | 37 |  |  |  | 1.5 | 0.256 | 1.756
P46459 | Letham (site 6) | Haddington | Medium | 8 | WHE | Taylor Wimpey | 22 | [5 empty] | 22 |  |  | 22 | 22 | 21 | 1 | amb | 22 | Y | 25/26 | [5 empty] | 0 | 22 |  |  |  |  | 22 | [5 empty] | 0
P46454 | Letham (site 6) | Haddington | Medium | 7 | WHE | Taylor Wimpey |  | 12 |  |  |  |  | 12 |  |  | 12 | 12 | 12 | 0 |  | 12 | Y | 25/26 | [5 empty] | 0 | 12 |  |  |  |  | 12 | [5 empty] | 0
P41575 | Letham M&M Ph 3 | Haddington | Medium | 5 | PfP | Springfield | 15 | [5 empty] | 15 |  |  | 15 | 15 | 13 | 2 | amb | 15 | Y | 26/27 | 15 |  |  |  |  | 15 |  | 15 |  |  |  | 15 | 1.92 |  |  |  |  | 1.92 | Chariatable bonds requested
P44879 | Mall Avenue | Musselburgh | High | 9 | WHE | Dundas |  | 11 |  |  |  |  | 11 |  |  | 11 | 11 | 8 | 3 | Ambulant | 11 | Y | 27/28 |  | 11 |  |  |  | 11 |  |  | 11 |  |  | 11 |  | 0.9 |  |  |  | 0.9
P41512 | Wallyford - Area 1 ph 1 | Wallyford | High | 8 | ELC |  | 36 | [5 empty] | 36 |  |  | 36 | 36 | 30 | 6 | Mix | 36 | Y | 26/27 | 36 |  |  |  |  | 36 |  | 36 |  |  |  | 36 | 1.1 | 1.326 |  |  |  | 2.426
P41699 | Wallyford - Area 1 ph 2 (SR) | Wallyford | High | 8 | ELC |  | 16 | [5 empty] | 16 |  |  | 16 | 16 | 12 | 4 | Mix | 16 | Y | 28/29 |  |  | 16 |  |  | 16 |  |  |  | 16 |  | 16 |  |  | 1.68 |  |  | 1.68
P41705 | Wallyford - Area 1 ph 2 (MMR) | Wallyford | High | 8 | ELC |  |  | 24 |  |  |  |  | 24 |  |  | 24 | 24 | 24 | 0 | Mix | 24 | Y | 28/29 |  |  | 24 |  |  | 24 |  |  |  | 24 |  | 24 |  |  | 1.68 |  |  | 1.68
P45493 | Wallyford - Area 5a | Wallyford | High | 9 | WHE | McTaggart | 29 | [5 empty] | 29 |  |  | 29 | 29 |  | 29 | Older People | 29 | Y | 21/22 | [5 empty] | 0 | 29 |  |  |  |  | 29 | [5 empty] | 0
P45494 | Wallyford - Area 5b | Wallyford | High | 9 | WHE | McTaggart |  | 61 |  |  |  |  | 61 |  |  | 61 | 61 |  | 61 |  | 61 | Y | 21/22 | [5 empty] | 0 | 61 |  |  |  |  | 61 | [5 empty] | 0
P46460 | Wallyford - Area 6a (SR) | Wallyford | Medium | 9 | WHE | McTaggart | 19 | [5 empty] | 19 |  |  | 19 | 19 | 17 | 2 | wh/chair | 19 | Y | 26/27 | 19 |  |  |  |  | 19 |  | 19 |  |  |  | 19 | 2.28 |  |  |  |  | 2.28
P43714 | Wallyford - Area 6a (MMR) | Wallyford | Medium | 9 | WHE | McTaggart |  | 9 |  |  |  |  | 9 |  |  | 9 | 9 | 9 | 0 |  | 9 | Y | 26/27 | 9 |  |  |  |  | 9 |  | 9 |  |  |  | 9 | 0.754 |  |  |  |  | 0.754
P41588 | Wallyford - Area 6b | Wallyford | Medium | 9 | WHE | McTaggart | 32 | [5 empty] | 32 |  |  | 32 | 32 | 30 | 2 | wh/chair | 32 | Y | 27/28 |  | 32 |  |  |  | 32 |  |  | 32 |  |  | 32 |  | 3.835 |  |  |  | 3.835
P45740 | Wallyford Primary School | Wallyford | High | 9 | ELC |  | 60 | [5 empty] | 60 |  |  | 60 | 60 | 54 | 6 | wh/chair | 60 | Y | 26/27 | 60 |  |  |  |  | 60 | 30 | 30 |  |  |  | 60 | 1.648 | 1 |  |  |  | 2.648
P47428 | Windygoul South Ph2 | Tranent | Medium | 6 | CRE | Springfield | 32 | [5 empty] | 32 |  |  | 32 | 32 | 26 | 6 | amb | 32 | Y | 27/28 |  | 32 |  |  |  | 32 |  |  | 32 |  |  | 32 |  | 4.097 |  |  |  | 4.097
P41595 | Windygoul South Ph3 | Tranent | Medium | 8 | ELHA | Springfield | 50 | [5 empty] | 50 |  |  | 50 | 50 | 36 | 14 | Mix | 50 | Y | 28/29 |  |  | 50 |  |  | 50 |  |  |  |  | 50 | 50 |  |  | 4.704 | 3.136 |  | 7.84
| OMPs |  | High |  | 10 | ELC | 20 | [5 empty] | 20 |  | 20 |  | 20 | 20 |  |  | 20 | N |  | 4 | 4 | 4 | 4 | 4 | 20 | 4 | 4 | 4 | 4 | 4 | 20 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 2
| Total | [5 empty] | 1182 | 162 | 0 | 0 | 0 | 0 | 1344 | 37 | 20 | 1287 | 1344 | 996 | 348 |  | 1344 |  |  | 166 | 240 | 305 | 210 | 126 | 1047 | 158 | 309 | 151 | 334 | 272 | 1224 | 17.113 | 18.566 | 27.008 | 26.207 | 19.474 | 108.368
[36 empty] | 9.386 | 7.04 | 4.693 | 3 | 3 | 27.119
[35 empty] | 25% slippage | 11.732 | 8.8 | 4.453 | 3.75 | 3.75 | 32.485
Drop Down Table Values
[22 empty] | Numerical Value | Geographic Code
[22 empty] | 1 | West Highland/Island Authorities/Remote/Rural Argyll -RSL - SR - Greener |  |  |  |  | RSL - SR - Greener
[22 empty] | 2 | West Highland/Island Authorities/Remote/Rural Argyll |  |  |  |  | RSL - SR - Other
[22 empty] | 3 | Other Rural |  |  |  |  | RSL - SR - Greener
[22 empty] | 4 | Other Rural |  |  |  |  | RSL - SR - Other
[22 empty] | 5 | City and Urban |  |  |  |  | RSL - SR - Greener
[22 empty] | 6 | City and Urban |  |  |  |  | RSL - SR - Other
[22 empty] | 7 | All |  |  |  |  | RSL - Mid-Market Rent - Greener
[22 empty] | 8 | All |  |  |  |  | RSL - Mid-Market Rent - Other
[22 empty] | 9 | All |  |  |  |  | Council - SR - Greener
[22 empty] | 10 | All |  |  |  |  | Council -SR - Other

## Table 1C ASHP Resource
MORE HOMES DIVISION
STRATEGIC HOUSING INVESTMENT PLAN 2026/27-2030/31
Table 1 - AFFORDABLE HOUSING SUPPLY PROGRAMME - Years 1-5 2026/27-2030/31
| LOCAL AUTHORITY: | EAST LOTHIAN COUNCIL
| PROJECT | SUB-AREA | PRIORITY | GEOGRAPHIC COORDINATES (X:EASTING Y:NORTHING) | GEOGRAPHIC CODE (Numeric Value - from Drop Down Table Below) | DEVELOPER | UNITS - TENURE | [6 empty] | UNITS - BUILT FORM |  |  |  | UNITS - TYPE |  |  |  | GREENER STANDARDS | APPROVAL DATE | UNITS SITE STARTS | [5 empty] | UNITS - COMPLETIONS | [5 empty] | SG AHSP FUNDING REQUIREMENT (£0.000M)
HARP Number |  |  | Low / Medium / High |  |  |  | Social Rent | Mid Market Rent | LCHO - Shared Equity | LCHO - Shared Ownership | LCHO - Improvement for Sale | PSR | Total Units | Rehab | Off the Shelf | NB | Total Units | GN | Specialist Provision | Type of Specialist Particular Need (If Known) | Total Units by Type | Enter Y or N | Financial Year (Estimated or Actual) | 26/27 | 27/28 | 28/29 | 29/30 | 30/31 | TOTAL SITE STARTS OVER PERIOD OF SHIP | 26/27 | 27/28 | 28/29 | 29/30 | 30/31 | TOTAL COMPLETIONS OVER PERIOD OF SHIP | 26/27 | 27/28 | 28/29 | 29/30 | 30/31 | TOTAL AHSP
P44897 | Blindwells area5 ph1 | Blindwells | High | 9 | ELHA | Persimmon | 52 | [5 empty] | 52 |  |  | 52 | 52 | 46 | 6 | mix | 52 | Y | 25/26 | [5 empty] | 0 |  | 52 |  |  |  | 52 | 5.152 |  |  |  |  | 5.152
P47385 | Blindwells Town Centre | Blindwells | High | 8 | PfP | PfP |  | 65 |  |  |  |  | 65 |  |  | 65 | 65 | 50 | 15 | elderly | 65 | Y | 28/29 |  |  | 65 |  |  | 65 |  |  |  | 65 |  | 65 |  | 0.78 | 2.475 | 2.476 |  | 5.731
P47382 | Blindwells area 4a | Blindwells | High | 8 | PfP |  | 42 | [5 empty] | 42 |  |  | 42 | 42 | 40 | 2 | wh/chair | 42 | Y | 24/25 | [5 empty] | 0 |  | 42 |  |  |  | 42 | 0.885 |  |  |  |  | 0.885 | Possible chariatable bond
P41846 | Blindwells area 6 ph 1 | Blindwells | Medium | 8 | ELC | Bellway | 23 | [5 empty] | 23 |  |  | 23 | 23 | 17 | 6 | mix | 23 | Y | 26/27 | 23 |  |  |  |  | 23 |  | 23 |  |  |  | 23 | 1.219 | 1.219 |  |  |  | 2.438
P41590 | Elphinstone West Phase 2 | Elphinstone | High | 5 | ELHA | Bellway | 28 | [5 empty] | 28 |  |  | 28 | 28 | 28 |  |  | 28 | Y | 25/26 | [5 empty] | 0 |  | 28 |  |  |  | 28 | 1.755 |  |  |  |  | 1.755
P42753 | Herdmanflat 1 | Haddington | High | 9 | ELC | Cruden | 51 | [5 empty] | 51 |  |  | 51 | 51 |  | 51 | Older People | 51 | Y | 25/26 | [5 empty] | 0 |  | 51 |  |  |  | 51 |  | 2.783 |  |  |  | 2.783
P42091 | Herdmanflat 1A | Haddington | High | 9 | ELC | Cruden | 57 | [5 empty] | 57 |  |  | 57 | 57 |  | 57 | Older People | 57 | Y | 27/28 |  | 57 |  |  |  | 57 |  |  |  | 57 |  | 57 |  |  | 3 | 3 |  | 6
P45740 | Wallyford Primary School | Wallyford | High | 9 | ELC |  | 60 | [5 empty] | 60 |  |  | 60 | 60 | 54 | 6 | wh/chair | 60 | Y | 26/27 | 60 |  |  |  |  | 60 | 30 | 30 |  |  |  | 60 | 1.648 | 1 |  |  |  | 2.648
P41512 | Wallyford - Area 1 ph 1 | Wallyford | High | 8 | ELC |  | 36 | [5 empty] | 36 |  |  | 36 | 36 | 30 | 6 | Mix | 36 | Y | 26/27 | 36 |  |  |  |  | 36 |  | 36 |  |  |  | 36 | 1.1 | 1.326 |  |  |  | 2.426
P46460 | Wallyford - Area 6a (SR) | Wallyford | Medium | 9 | WHE | McTaggart | 19 | [5 empty] | 19 |  |  | 19 | 19 | 17 | 2 | wh/chair | 19 | Y | 26/27 | 19 |  |  |  |  | 19 |  | 19 |  |  |  | 19 | 2.28 |  |  |  |  | 2.28
P43714 | Wallyford - Area 6a (MMR) | Wallyford | Medium | 9 | WHE | McTaggart |  | 9 |  |  |  |  | 9 |  |  | 9 | 9 | 9 | 0 |  | 9 | Y | 26/27 | 9 |  |  |  |  | 9 |  | 9 |  |  |  | 9 | 0.754 |  |  |  |  | 0.754
P41588 | Wallyford - Area 6b | Wallyford | Medium | 9 | WHE | McTaggart | 32 | [5 empty] | 32 |  |  | 32 | 32 | 30 | 2 | wh/chair | 32 | Y | 27/28 |  | 32 |  |  |  | 32 |  |  | 32 |  |  | 32 |  | 3.835 |  |  |  | 3.835
| Total | [5 empty] | 400 | 74 | 0 | 0 | 0 | 0 | 474 | 0 | 0 | 474 | 474 | 321 | 153 |  | 474 |  |  | 147 | 89 | 65 | 0 | 0 | 301 | 30 | 290 | 32 | 122 | 0 | 474 | 14.793 | 10.943 | 5.475 | 5.476 | 0 | 36.687
[36 empty] | 9.384 | 7.04 | 4.693 | 3 | 3 | 27.117
[35 empty] | 25% slippage | 11.73 | 8.8 | 4.453 | 3.75 | 3.75 | 32.483
[22 empty] | Drop Down Table Values | [14 empty] | 1.534 | 5.379
[22 empty] | Numerical Value | Geographic Code
[22 empty] | 1 | West Highland/Island Authorities/Remote/Rural Argyll -RSL - SR - Greener |  |  |  |  | RSL - SR - Greener
[22 empty] | 2 | West Highland/Island Authorities/Remote/Rural Argyll |  |  |  |  | RSL - SR - Other
[22 empty] | 3 | Other Rural |  |  |  |  | RSL - SR - Greener
[22 empty] | 4 | Other Rural |  |  |  |  | RSL - SR - Other
[22 empty] | 5 | City and Urban |  |  |  |  | RSL - SR - Greener
[22 empty] | 6 | City and Urban |  |  |  |  | RSL - SR - Other
[22 empty] | 7 | All |  |  |  |  | RSL - Mid-Market Rent - Greener
[22 empty] | 8 | All |  |  |  |  | RSL - Mid-Market Rent - Other
[22 empty] | 9 | All |  |  |  |  | Council - SR - Greener
[22 empty] | 10 | All |  |  |  |  | Council -SR - Other

## TABLE 2 - HIF PROJECTS
MORE HOMES DIVISION
STRATEGIC HOUSING INVESTMENT PLAN 2026/27-2030/31
Table 2 - HOUSING INFRASTRUCTURE FUND (HIF) PROJECTS
Note: Projects should be entered as either Grant or Loan - Any which state a mixed category e.g. Grant/Loan or Grant or Loan will not be considered
TABLE 2.1 - GRANT PROJECTS
[9 empty] | AFFORDABLE HOUSING UNITS DIRECTLY PROVIDED BY INFRASTRUCTURE FUNDING - BY ESTIMATED COMPLETION DATE | [14 empty] | HIF GRANT FUNDING REQUIRED |  |  |  |  | POTENTIAL ADDITIONAL CAPACITY - UNITS NOT DIRECTLY FUNDED BUT UNLOCKED BY INFRASTRUCTURE FUNDING
PROJECT | PRIORITY | GEOGRAPHIC COORDINATES (X:EASTING Y:NORTHING) | APPLICANT | PLANNING STATUS (OUTLINE/ MASTERPLAN/ FULL CONSENT IN PLACE) (Y/N) | DOES APPLICANT OWN OR HAVE POTENTIAL TO OWN THE SITE? (Y/N) | CURRENT SITE OWNER | BRIEF DESCRIPTION OF WORKS FOR WHICH INFRASTRUCTURE FUNDING IS SOUGHT (PROVIDE WORK HEADINGS - DO NOT INSERT "INFRASTRUCTURE WORKS") | IS PROJECT LINKED TO DIRECT PROVISION OF AFFORDABLE HOUSING? (Y/N) | AFFORDABLE |  |  |  |  | MARKET |  |  |  |  | PRIVATE RENT
| Low / Medium / High | [7 empty] | 2026/27 | 2027/28 | 2028/29 | POST 2029/30 | AFFORDABLE TOTAL OVER PLAN OVER SHIP PERIOD | 2026/27 | 2027/28 | 2028/29 | POST 2029/30 | MARKET TOTAL OVER PLAN OVER SHIP PERIOD | 2026/27 | 2027/28 | 2028/29 | POST 2029/30 | PRIVATE RENT TOTAL OVER PLAN OVER SHIP PERIOD | 2026/27 | 2027/28 | 2028/29 | POST 2029/30 | TOTAL HIF GRANT FUNDING REQUIRED | UNITS - POTENTIAL ADDITIONAL CAPACITY IN EITHER LATER PHASES OR OTHER SITES | TENURE - AFFORDABLE / MARKET /PRIVATE RENTED
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Total | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TABLE 2.2 - LOAN PROJECTS
[9 empty] | AFFORDABLE HOUSING UNITS DIRECTLY PROVIDED BY INFRASTRUCTURE FUNDING - BY ESTIMATED COMPLETION DATE | [14 empty] | HIF LOAN FUNDING REQUIRED |  |  |  |  | POTENTIAL ADDITIONAL CAPACITY - UNITS NOT DIRECTLY FUNDED BUT UNLOCKED BY INFRASTRUCTURE FUNDING
PROJECT | PRIORITY | GEOGRAPHIC COORDINATES (X:EASTING Y:NORTHING) | APPLICANT | PLANNING STATUS (OUTLINE/ MASTERPLAN/ FULL CONSENT IN PLACE) (Y/N) | DOES APPLICANT OWN OR HAVE POTENTIAL TO OWN THE SITE? (Y/N) | CURRENT SITE OWNER | BRIEF DESCRIPTION OF WORKS FOR WHICH INFRASTRUCTURE FUNDING IS SOUGHT (PROVIDE WORK HEADINGS - PLEASE "INFRASTRUCTURE WORKS") | IS PROJECT LINKED TO DIRECT PROVISION OF AFFORDABLE HOUSING? (Y/N) | AFFORDABLE |  |  |  |  | MARKET |  |  |  |  | PRIVATE RENT
| Low / Medium / High | [7 empty] | 2018/19 | 2019/20 | 2020/21 | POST 2020/21 | AFFORDABLE TOTAL OVER PLAN OVER SHIP PERIOD | 2018/19 | 2019/20 | 2020/21 | POST 2020/21 | MARKET TOTAL OVER PLAN OVER SHIP PERIOD | 2018/19 | 2019/20 | 2020/21 | POST 2020/21 | PRIVATE RENT TOTAL OVER PLAN OVER SHIP PERIOD | 2018/19 | 2019/20 | 2020/21 | POST 2020/21 | TOTAL HIF LOAN FUNDING REQUIRED | UNITS - POTENTIAL ADDITIONAL CAPACITY IN EITHER LATER PHASES OR OTHER SITES | TENURE - AFFORDABLE / MARKET /PRIVATE RENTED
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Total | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## TABLE 3 - HIF AFFORDABLE HSG
MORE HOMES DIVISION
STRATEGIC HOUSING INVESTMENT PLAN 2026/27-2030/31
Table 3 - POTENTIAL HIF AFFORDABLE HOUSING PROJECTS WHICH MAY BE DEVELOPED FOLLOWING HIF INVESTMENT
LOCAL AUTHORITY:
PROJECT | SUB-AREA | PRIORITY | GEOGRAPHIC COORDINATES (X:EASTING Y:NORTHING) | GEOGRAPHIC CODE (Numeric Value - from Drop Down Table Below) | DEVELOPER | UNITS - TENURE | [6 empty] | UNITS - BUILT FORM |  |  |  | UNITS - TYPE |  |  |  | GREENER STANDARDS | APPROVAL DATE | UNIT SITE STARTS |  |  |  |  | UNITS - COMPLETIONS |  |  |  |  | SG AHSP FUNDING REQUIREMENT (£0.000M)
|  | Low / Medium / High |  |  |  | Social Rent | Mid Market Rent | LCHO - Shared Equity | LCHO - Shared Ownership | LCHO - Improvement for Sale | PSR | Total Units | Rehab | Off the Shelf | NB | Total Units | GN | Specialist Provision | Type of Specialist Particular Need (If Known) | Total Units by Type | Enter Y or N | Financial Year (Estimated or Actual) | 2025/26 | 2026/27 | 2027/28 | POST 2028/29 | TOTAL SITE STARTS OVER PERIOD OF SHIP | 2025/26 | 2026/27 | 2027/28 | POST 2028/29 | TOTAL COMPLETIONS OVER PERIOD OF SHIP | 2025/26 | 2026/27 | 2027/28 | POST 2028/29 | TOTAL AHSP FUNDING REQUIRED OVER SHIP PERIOD
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drop Down Table Values
[21 empty] | Numerical Value | Geographic Code
[21 empty] | 1 | West Highland/Island Authorities/Remote/Rural Argyll -RSL - SR - Greener |  |  |  | RSL - SR - Greener
[21 empty] | 2 | West Highland/Island Authorities/Remote/Rural Argyll |  |  |  | RSL - SR - Other
[21 empty] | 3 | Other Rural |  |  |  | RSL - SR - Greener
[21 empty] | 4 | Other Rural |  |  |  | RSL - SR - Other
[21 empty] | 5 | City and Urban |  |  |  | RSL - SR - Greener
[21 empty] | 6 | City and Urban |  |  |  | RSL - SR - Other
[21 empty] | 7 | All |  |  |  | RSL - Mid-Market Rent - Greener
[21 empty] | 8 | All |  |  |  | RSL - Mid-Market Rent - Other
[21 empty] | 9 | All |  |  |  | Council - SR - Greener
[21 empty] | 10 | All |  |  |  | Council -SR - Other

## TABLE 4 - NON-AHSP PROJECTS
MORE HOMES DIVISION
STRATEGIC HOUSING INVESTMENT PLAN 2026/27-2030/31
LOCAL AUTHORITY: | East Lothian
TABLE 4 - AFFORDABLE HOUSING PROJECTS FUNDED OR SUPPORTED BY SOURCES OTHER THAN THE RPA/TMDF BUDGET
PROJECT ADDRESS | SUB-AREA | PRIORITY | GEOGRAPHIC COORDINATES (X:EASTING Y:NORTHING) | DEVELOPER | FUNDING SUPPORT SOURCE | APPROVAL DATE |  |  |  |  | TOTAL |  |  |  |  | TOTAL UNIT COMPLETIONS | NON SG FUNDING TOTAL £0.000M | OTHER NON-AHSP SG FUNDING (IF APPLICABLE) £0.000M | TOTAL FUNDING £0.000M
|  | Low / Medium / High |  |  |  | Financial Year (Actual or Estimated) | 2026/27 | 2027/28 | 2028/29 | 2029/30 | TOTAL SITE STARTS | 2026/27 | 2027/28 | 2028/29 | 2029/30
Hallhill North | Dunbar | High |  | Taylor Wimpey | Private | [6 empty] | 36 |  |  |  | 36 |  |  | 0
Total | [6 empty] | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 36 | 0 | 0 | 0

## Table 5- CT & Developer Cont
MORE HOMES DIVISION
STRATEGIC HOUSING INVESTMENT PLAN 2026/27-2030/31
LOCAL AUTHORITY:
TABLE 5.1: COUNCIL TAX ON SECOND AND EMPTY HOMES(£0.000M)
| TAX RAISED OR IN HAND | TAX USED TO SUPPORT AFFORDABLE HOUSING | TAX CARRIED FORWARD TO SUBSEQUENT YEARS
PRE - 23 | 1.174
2024/2025 | 1.624 | 0.508 | 1.116
2025/26 | 2.379 | 0 | 2.379
TABLE 5.2: DEVELOPER CONTRIBUTIONS (£0.000M)
| SUMS |  |  | UNITS
| RAISED OR IN HAND | USED TO ASSIST HOUSING | SUM CARRIED FORWARD TO SUBSEQUENT YEARS | AFFORDABLE UNITS FULLY FUNDED FROM CONTRIBUTIONS | UNITS PARTIALLY ASSISTED FROM CONTRIBUTIONS | UNITS TOTAL
PRE - 24 | 0.37
2024/25 | 0.37 | 0.37 | 0 | 0.319 | 5 | 5.319
2025/26
Note: These tables are used to capture financial information. Details of how this has been used to fund/assist affordable housing should be contained in the text of the SHIP as described in the guidance.