## Appendix 1
Appendix 1 - East Lothian Council Retention Policy Statement - 31.08.24 1, 2, 3, 4
1 | Policy on retention in construction contracts is as set out below with respect to Chapter 17 in Handbook 1
of The Client Guide to Construction Projects
| 1.1 | Derived directly and solely from it | Yes | No
please state why here 5
| 1.2 | Derived from it and other sources | Yes | No
please identify these here
| 1.3 | Diverges from it | Yes | No
The Council will apply standard retention percentages in most circumstances The Council will hold retention for 12 months after Practical Completion in most circumstances The Council will not consider taking on unnecessary risk The Council does not operate Project Bank Accounts
| 1.4 | Not required to and does not follow it | Yes | No
please state why and what your policy is here
| 1.5 | Other | Yes | No
please describe here
2 | The strategic approach to retention taken by East Lothian Council is as set out below
| 2.1 | Aims for the contractor to deliver zero defects | Yes | No
To ensure high standards of workmanship, to facilitate the handover proceedure and to minimise disruption to end users of the building after hand over
| 2.2 | Retention is applied in all construction contracts regardless of project-specific factors | Yes | No
See item 2.5 below
| 2.3 | Retention is applied uniformly in all construction contracts regardless of project-specific factors | Yes | No
Each construction project will be reviewed and assessed on an individual project basis to determine the value of retention to be held.
| 2.4 | Some construction contracts apply retention | Yes | No
All construction projects will be subjected to retention apart from those noted in 2.5 below
| 2.5 | Some construction contracts do not apply retention | Yes | No
Each construction project will be reviewed and assessed on an individual project basis. The following project types may not be considered suitable for retention:- Works procured via certain Frameworks where Framework conditions exclude retention, Low value works, Demolition contracts where there is no reinstatement or retention of structures and other unforseen situations where retention is not deemed appropriate
| 2.6 | Other | Yes | No
please describe here
3 | Policy on retention in construction contracts takes account of the following factors
| 3.1 | Project type | Yes | No
Each construction project will be reviewed and assessed on an individual project basis to determine the value of retention to be held.
| 3.2 | Project value | Yes | No
Each construction project will be reviewed and assessed on an individual project basis to determine the value of retention to be held.
| 3.3 | Project duration | Yes | No
Each construction project will be reviewed and assessed on an individual project basis to determine the value of retention to be held.
| 3.4 | Project design complexity and/or novelty including ergonomics | Yes | No
and buildability
Each construction project will be reviewed and assessed on an individual project basis to determine the value of retention to be held.
| 3.5 | Extent of off-site and on-site work specified or implied by the design | Yes | No
Each construction project will be reviewed and assessed on an individual project basis to determine the value of retention to be held.
| 3.6 | Availability of project materials and associated trade skillsets for the | Yes | No
required standard of finish
Each construction project will be reviewed and assessed on an individual project basis to determine the value of retention to be held.
| 3.7 | Project procurement route, see Handbook 2 Chapter 5 of | Yes | No
The Client Guide to Constructipon Projects
Each construction project will be reviewed and assessed on an individual project basis to determine the value of retention to be held.
| 3.8 | Project procurement procedure, see Chapter 2 Section 3 of | Yes | No
The Public Contracts (Scotland) Regulations 2015
Each construction project will be reviewed and assessed on an individual project basis to determine the value of retention to be held.
| 3.9 | Form of contract | Yes | No
The treatment of retention will be governed and managed by the relevant Conditions of Contract. The percentage of retention to apply will be stated in the contract documents
| 3.1 | Volume, detail and format of as-built, operating and maintenance | Yes | No
information, including compliance with BIM requirements
H&S File, O&M Manuals and appropriate BIM information should be completed in full and submitted to the Employer before the full amount of half retention is released at PC. The Council may continue to hold a pre determined amount untill all completion documentation has been approved and submitted
| 3.11 | Market conditions | Yes | No
Each construction project will be reviewed and assessed on an individual project basis to determine the value of retention to be held.
| 3.12 | Availability and affordability of a trust-based commercial bank account | Yes | No
into which the main contractor can deposit subcontractors’ retention
The Council do not operate Project Bank Accounts at this time
| 3.13 | Inspection and testing regime for materials and workmanship on site | Yes | No
An appropriate amount of retention may continue to be withheld at Practical Completion and /or End of Defects until any substandard workmanship , materials or equipment have been satisfactorily made good
| 3.14 | Targeting distinct activities/trades/elements for specific retention treatment | Yes | No
May be considered. Each construction project will be reviewed and assessed on an individual project basis to determine the Council's approach to retention .
| 3.15 | Implementing a payment process triggered by demonstrable | Yes | No
milestone events on site instead of set intervals of time
May be considered. Each construction project will be reviewed and assessed on an individual project basis to determine the Council's approach to retention .
| 3.16 | Holding no retention on temporary works procured directly by the public | Yes | No
contract that will not be permanently incorporated into the completed works
May be considered. Each construction project will be reviewed and assessed on an individual project basis to determine the Council's approach to retention .
| 3.17 | Enabling the replication of main contract retention provisions in successive | Yes | No
contracts along the supply chain as far as reasonably possible
The Council encourages fair and reasonable sub contractor conditions of contract including the alignment of sub contractor retention levels with those of the main contract
| 3.18 | Other factor(s) | Yes | No
please describe here
Notes
1 The Retention Policy Statement is to be published online by 31 August 2024 then reviewed and where necessary revised by
each subsequent 31 August thereafter (intermittent publication between annual statements also permissible e.g. when a
policy change is deemed significant by the public body).
2 Please answer all circumstances that apply and avoid confining responses to given lines and parameters where others
might apply also or instead.
3 Please e-mail propertyandconstruction@gov.scot to obtain a copy of this template and to have the completed Retention
Policy Statement linked to in Scottish Government’s directory.
4 Please also consider placing a link to the directory on your website.
5 Overwrite existing text with your information in all such instances.