## Action Plan
East Lothian Heat and Energy Efficiency Delivery Plan - 2024-2028
Ref | Intervention | Outcome | Target dates | Lead Service | Indicator | Baseline | UPDATE | RAG Tracker | Notes
Outcome 1 - Property owners are engaged with the need to reduce carbon emissions and empowered to make decisions on energy efficiency and heating solutions
Key Priority Area 1: Raising Awareness
1 | Increase awareness among home and business owners of the urgent need to plan for changes to how their property is heated | Campaigns to raise awareness | ongoing | Scot Gov / Community | Change in survey responses | Determined by community surveys
2 | Increase awareness among home and business owners of available funding resources and support for installing energy efficiency improvements | Funding secured for retrofit |  | Community / HES / BES | HES enquiries, Grants awarded - quantity and value | 2023 statistics
Key Priority Area 2: Building Community Leadership
3 | Identify action groups and volunteers in each community to take a local leadership role | Key groups identified | end 2024 | Community | No. of groups / volunteers committed | Existing ELCAN network
4 | Establish data management and sharing procedures to facilitate data collection and community-based activities | Agreement process in place | end 2024 | Community/ LHEES | Data agreements in place | New initiative
5 | Agree action plans for each community to support energy efficiency drive and where appropriate, preparation for heat networks | First by June 2024 | ongoing | Community | No. of plans in agreed | New initiative
6 | Undertake a programme of resident surveys and thermal imaging work to raise awareness and improve data on energy use and heating | Increasing accurate data coverage | ongoing | Community | Survey responses Properties imaged | New initiative
Outcome 2: East Lothian's homes and buildings are as energy efficient as possible
Key Priority Area 1: Conservation Areas
7 | Agree advice on energy efficiency measures that can be provided to all owners of properties in Conservation Areas | Website updated | end 2024 | Planning / LHEES |  | New initiative
8 | Deliver free pre-application advice for Conservation Area properties with proposals for renewables and/or energy efficiency measures to encourage early action | Increase in adaptions in Cons. Areas | ongoing | Planning / Community | No. of enquiries received | New initiative
Key Priority Area 2: Solar PV Installations
9 | Track number of properties with solar PV and batteries, prioritising those suitable for communal and individual heat solutions | 10000 PV, 500 Batteries | 2028 | LHEES / Community | MCS registrations | SPV 5116 at end 2023, 915 new PV in 2023, 14 new batteries (no accurate record of earlier battery installations) | 429 to end Aug 2024 |  | Majority linked with new build, not retrofit
Key Priority Area 3: Owner-occupiers
10 | Ensure Scot Gov EES:ABS funding for vulnerable households is targeted effectively and aligns with any heat network expansion timeline | Full budget spent annually | ongoing | Housing | Annual plan to spend all funds available | £1.1m in 2022/23 and 2023/24 |  |  | £1.1m again in 24/25 though late decision - 15 Solar PV & battery properties, 12 properties for EWI and a CWI project in Wallyford
11 | Working with community action teams, deliver community driven programme promoting improved insulation, building on survey work and highlighting potential savings | To be decided |  | Community / HES | HES enquiries | 509 enquiries in Q4 2023
Key Priority Area 4: Council Homes
12 | Continue to deliver a rolling programme of fabric upgrades to improve energy efficiency | Targets to be determined - see below | ongoing | Housing | EPC and condition reports
13 | Monitor the outcome of the Scottish Government consultation on Net Zero Standard and the implication for fabric improvement priorities |  | end 2024 | Housing | To be confirmed
14 | Promote Solar PV and battery options for properties that may be suitable for communal and individual heat solutions |  | ongoing | Housing
Key Priority Area 5: Private Rented and Short Term Lets
15 | Agree procedure and responsibility for enforcing new legislation on minimum EPC standards |  | End 2024 | LHEES / Licensing / Housing | Home Analytics and Private Landlord Register | 772 without EPC and 2179 rated below EPC C
16 | Proactively target owners of poor performing with warnings and energy efficiency advice ahead of EPC changes | To be set in late 2024 based on Scot Gov advice |  | EST / LHEES / Licensing / Housing | EPC quarterly updates and Private Landlord Register | As above
Key Priority Area 6: Social Rented
17 | Engage all Housing Associations regarding interest in potential heat network connection opportunities |  | To be decided following feasibility | LHEES / Housing |  | ELHA and Homes for Life engaged
18 | Explore options for socially rented properties that may be suitable for communal heat network/pump connection | To be decided |  | LHEES | Number of properties connecting | New initiative - 125 with electric heating
Key Priority Area 7: Council-owned Non-domestic
19 | Identify assets that could be served by a heat network, following the Asset Review | Property list | End 2024 | LHEES / Assets | Number of properties | 77 on-gas sites prior to the review
20 | Prioritise energy efficiency investment for these properties with a pipeline of possible projects to take advantage of funding opportunities |  | ongoing | Assets | HNR tracker / Annual gas use | Initial list produced in 2023
21 | Prepare net zero plans for Council assets currently using LPG or oil for heating |  | mid 2025 | Assets | Number remaining to convert | 7 properties outstanding
22 | Extend the preparation of Council assets to those that are leased to other businesses |  |  | LHEES / Estates | Number requiring action | Unknown - still being explored
Key Priority Area 8: Other Non-domestic
23 | Encourage all businesses to explore and prioritise energy efficiency measures | Improvements in EPCs | Ongoing | Econ Dev / Community / BES | Businesses engages with BES | Projects already completed
Outcome 3 - Heat solutions are delivered to tackle fuel poverty and meet 2045 net zero target
Key Priority Area 1: Heat Network Opportunities
24 | Work with Midlothian, Edinburgh, West Lothian and Fife Councils on a regional heat masterplan, exploring the potential demand for heat and heat network connections across the region | Phase 1 completed | 2025-03-01 | LHEES | Report and GIS visualisation | LHEES reports
25 | Subject to securing funding, undertake strategic feasibility work on a range of local heat solutions | Report completed | mid 2025 | LHEES | Report completed | New Initiative
26 | Maintain contact with all relevant external partners and stakeholders related to heat network opportunities while feasibility studies are being carried out | regular communications | ongoing | LHEES | List of engaged stakeholders | List from LHEES report
27 | Determine any phases of heat network development based on the outcomes of feasibility studies | Early phase options agreed | TBC | LHEES / Community | Number of phases under consideration | New Initiative
Key Priority Area 2: Communal and Individual Heat Solutions
28 | Identify groups of properties that might be suitable for communal heat networks such as shared air source or ground source | Will be clarified by end 2024 |  | LHEES / Community | No. of identified leads | Biomass solutions already operational
29 | Engage residents and refer community groups to Community Energy Scotland for targeted advice |  | ongoing | Community / CES | Successful applications for CES funding | Pencaitland, Innerwick and Tyninghame
30 | Refer decision makers for individual solutions to Home Energy Scotland for targeted advice |  | ongoing | Community | HES quarterly reports to ELC
31 | Track the levels of air source and ground source heat pump installations | Quarterly reporting | ongoing | LHEES | MCS registrations | ASH - 458 total at end 2023, 69 new in 2023 GSH - 53 total at end 2023, 1 new in 2023 | 81 new ASH and 2 GSH by end Aug 2024 |  | 79 ASH to end Aug 2024. Sunamp trial may boost retrofit figures in 2024/25
Outcome 4 - Investment and grant funding is secured to deliver net zero projects
Key Priority Area 1: Feasibility Studies
32 | Secure funding to undertake a regional energy masterplan study | Funding secured from UKSPF | 2024-07-01 | LHEES / Fife / Edin / Mid | Funding secured |  |  |  | Phase 1 approved, potential for second in 25/26
33 | Secure funding from Heat Network Fund for a strategic level feasibility study on Heat Network proposals |  | 2024-05-01 | LHEES | Funding secured |  |  |  | Application delayed due to 24/25 budget spent
Key Priority Area 2: Infrastructure Investment
34 | Develop business plans for each phase of heat network development | Plans produced and agreed | TBC | TBC | Plans prepared
Key Priority Area 3: Grant funding from Scottish and UK Governments
35 | Secure annual funding from Scottish Government for ongoing energy efficiency programmes | April each year |  | Housing | Budget approved | £1.1m secured in 2023/24 |  |  | £1.1 secrured again for 24/25
36 | Develop a pipeline of ELC projects that can apply for ongoing rounds of capital funding via the Public Sector Heat Decarbonisation Fund | Revise list by end 2024 |  | Assets | Number of applications made and grants secured | New initiative |  |  | No funding available in 2024/25
Key Priority Area 4: Community Funding
37 | Support an application to the National Lottery Climate Action Fund to support Community Heat Team expansion | Phase 1 Submission | TBC | Community / LHEES | Application success | New initiative
38 | Support efforts by the Association of East Lothian Community Councils to coordinate community benefits from energy companies that support the development of local heat solutions | Ongoing |  | Community / LHEES | Number of agreements and annual value | New charity established in Feb 2024 |  |  | Early engagement underway with early promise
Outcome 5 - A significant proportion of the benefits of net zero investment remain within the East Lothian economy
Key Priority Area 1: Community Wealth Building
39 | Subject to feasibility studies, investigate and decide on the most appropriate corporate structure to develop and manage East Lothian's heat networks and other energy infrastructure | Timing dependant on feasibility work | end 2025 | LHEES / HNSU / Community | Delivery model agreed | Early investigations into Community Benefit Company / Cooperative
Key Priority Area 2: Tackling Fuel Poverty
40 | Aim for a delivery model for heat networks with no connection costs to ensure all customers can benefit from lower costs and net zero solutions |  | end 2025 | LHEES | Delivery model agreed
41 | Explore opportunities with credit unions to develop local loan solutions for retrofit work |  | end 2025 | LHEES | Number of applications made | New initiative
Key Priority Area 3: Developing the Local Supply Chain
42 | Increase the number of skilled installers in the region, to help towards closing the skills gap for both energy efficiency and any future heat network installation | To be decided following feasibility |  | Econ Dev | Number of companies involved | Output from Regional project on skills
Lead Service Key:
HES - Home Energy Scotland; BES - Business Energy Scotland; CES - Community Energy Scotland; LHEES - LHEES Officer at East Lothian Council