East Lothian Carers Strategy – Action Plan  2024-‘25

We said, we did…

2024/25

The East Lothian Carers Strategy was developed with the intention of supporting carers to manage their caring responsibilities with confidence and in good health, and that they are able to have a life of their own.

While the strategy outlines our vision for carers and the seven outcomes we want to achieve, the Action Plan outlines the practicalities of how these will be delivered.  Implementation of the actions within the plan will be led by the Carers Change Board, with support and feedback from carers and carers representatives.

Work on these actions will take place over this year and will only be achieved by continuing to build on the joint working that is already taking place, not just with our local carers organisations but with departments across the council, the NHS, and the wider community.

| Outcome 1: Carers are identified and can access support |  |  |
| --- | --- | --- |
| We said | We did | Who/Co-ordinator |
| Implement audit process for completed ACSP’s including feedback mechanism for information on where Carers Outcomes cannot be met | In place and discussed as part of contract monitoring. Report on outcomes that cannot be met included as part of audit process not highlighting many as often ACSP submitted at time of request so outcome unknown at that point. Meaningful information should come as part of more regular and embedded review process. | Carers Strategy Officer and CoEL |
| Continue to use Viewpoint to complete Young Carer Statements and use it to generate reports on YC Wellbeing and UNCRC Outcomes | Viewpoint supported the creation of 260 YCS and 6 monthly reports | Young Carers Service |
| Continue to make carers information more visible and easily accessible | Continuing, online content reviewed annually as part of carers week campaign or if significant changes | Carers Strategy Officer, Corporate Communications Team |
| Continue to review and update ELC Young Carers Website to ensure it is visible and easily accessible to all | Website was reviewed on a quarterly basis and new information added as and when required | Coordinator YC, Corporate Communications Team |
| Develop a communications plan to publicise key messages | Developed annually. Key communications around Carers week, Carers rights day and Young Carers Action Day | Carers strategy officer, Corporate Communications Team |
| Work with our partners in primary care to encourage carer identification and increase signposting to sources of information and support | Carers strategy officer and young carers co-ordinator both presented at practice managers meeting to make progress towards this outcome. Members of carers panel now working to share examples of good practice and support practices to make small changes that can be effective in supporting carers | ELHSCP and CoEL carers panel |
| Improve identification of carers in our community hospitals to identify carers, increase recognition of carers value throughout the persons stay and to support successful discharge planning | Ward based hospital link worker role agreed and worker in place from June 2024. Very successful pilot project, feedback shared with Carers change board in Oct 2024 and from ward perspective in April 2025. Funding to develop this role and increase reach through hospital volunteers as Carer Champions agreed for further two year period. Hospital discharge has been the focus of a huge piece of work with additional investment from Scottish Government. Called ‘home first’, this enhanced approach focuses on assessment and rehabilitation out with the hospital environment making raising awareness of carer involvement even more important at this time. Carer involvement is already a legal duty and well described in relevant policies so focus has been on practice, increasing staff awareness through think carer training and hospital link worker role. | ELHSCP and CoEL |
| Work within communities to raise awareness of carers, referral pathways and their need for support | Continued promotion of our carer support services through communications direct to the public and with partners. | ELHSCP and partners |
| Work with our community partners to increase carer identification, including Day centres, sheltered housing, large employers and schools | Focus for this year on employers. Promotion of carer positive events and working with local businesses to raise awareness of unpaid carers through our Proud to Care campaign in carers week 2024 and ongoing as part of the launch of Respitality in East Lothian. | ELHSCP and partner organisations |
| Our Young Carers service will continue their work with Associated Schools Groups and local C&YP services to identify Young Carers | An additional 270 YC were identified. | East Lothian Councils Young Carers Service and Education |
| Work with children’s services to increase identification of Young and Parent Carers in the Childs Planning Process and the role of the named person in particular working closely with schools, health visitors etc | Young Carers Service co-ordinator takes opportunities to increase identification of young and parent carers. Parent carer support workers from CoEL attended children and disabilities team meeting as well as presenting at wider childrens services briefing session to refresh links and raise awareness as well a | ELHSCP and Children’s services |
| Research models of implementation of Carer ID schemes, whether this should be done on local or national level | Discussed with many local areas and partners who have implemented similar schemes. Review showed most efficient way to produce cards is through East Lothian Council Smart Card Team, process to be agreed and begin in 2025/’26. CoEL key to working with local businesses and attracting partnerships to support carers | ELHSCP, national carers organisations and CoEL |
| Young Carers to decide if ID scheme is a priority now costs established | YC ID process agreed and first cards issued in Feb 25, communications around the launch as part of Young Carers Action Day. | ELHSCP and partner organisations |
| Consider barriers to different groups identifying and accessing support, including men, different ethnic groups, LGBT people and those with other protected characteristics | Focus on LGBT carers, Young Carers service links with MYPAS to ensure support available for Young Carers with worries around LGBT Promote peer support opportunity for LGBT carers through LGBT Health and Well being lgbthealth.org.uk | ELHSCP and partner organisations |

| Outcome 2: Carers are well informed and have access to tailored and age appropriate information and advice throughout their caring role |  |  |
| --- | --- | --- |
| We said | We did | Who/Co-ordinator |
| Continue to commission services to enable all carers in East Lothian to have access to advice and support throughout their carers journey on wide range of issues | New contract awarded to CoEL, through competitive tender process, for adult carer support in East Lothian on a longer term contract to provide stability for carers, beginning in June 2025 | ELHSCP |
| Review these contracts to ensure delivery of quality services to carers | Process already in place for quarterly reporting and contract monitoring with providers. As part of new contract for adult carer support development of Outcome based reporting agreed. | Carers Strategy Officer |
| Review numbers of Carers accessing advice and information services | 1134 individual carers supported in the 6 month period from October 2024 to end of March 2025 Information shared with over 5000 carers through regular mailings. | Carers Strategy Officer |
| Monitor numbers of ACSP’s and YCS being completed | 177 ACSP’s completed in 2024/’25 Carers accessing advice and information directly as above, in total information for carers shared with over 5000 carers through Carers of East Lothians regular mailing list 260 YCS completed through viewpoint, over 700 Young Carers now registered with the service | Carers Strategy Officer |
| Look at ways to offer support for carers to manage stress and distress behaviours while supporting people at home | PDS groups led by Alzheimers Scotland are now offered to everyone diagnosed with dementia. Two groups were delivered in different localities over 2024/’25 and 100% of attendees went on to take up the offer of one to one post diagnostic support from Alzheimers Scotland. Explored education around stress and distress with East Lothian Care Home Assessment and Support Team, no capacity within this or the Community Mental Health Team to extend education to carers. Large resource available from NHS Education for Scotland (NES) Responding to distress and distress in dementia resource – guide for carers. Potential to use this as a starting point to developing a smaller resource with support from NHS Lothian dementia nurse consultant. | ELHSCP, Learning and development, ELCHASE team, NHS Lothian, NES |
| Continue to develop clear pathways for carers to access both direct support and help developing an Adult Carer Support Plan (ACSP) or Young Carers Statement (YCS) | Continuing, pathways well established and good awareness from teams of how to access these but continue to promote. | Carers Strategy Officer, CoEL, Young Carers Service |
| Develop range and availability of materials available to Carers, CoEL to launch online peer support forum this year | Increasing range of materials available. Many printed and online resources, additional sources of information include: Carer education programme piloted at Dementia Cafes in 2024/’25 Videos for Carers rights day Peer support forum to launch summer 2025 | ELHSCP and partner organisations |
| Continue to provide advice, information and support to maximise incomes for carers (and the people they care for) | ELC’s financial inclusion team support aim to ensure people get the financial support they are entitled to and work closely with CoEL as well as other partners such as citizens advice to maximise access to benefits. They have regular contact with CoEL to share information and ensure carer support workers have the information to support carers for example through the financial assessment process for care at home. Carers continue to receive advice, information and support through CoEL’s welfare rights service. 78 YC families were supported to apply for benefits or issued with small hardship payments from YC budget. | CoEL, Young Carers Service and ELC’s Financial inclusion team |
| Monitor Carers access to benefits through CoEL support services | Over the most recent 6 month reporting period (Oct 2025-March 2025) 289 carers received welfare rights advice from Carers of East Lothian and an additional 202 accessed their benefits enquiry helpline. | Carers Strategy Officer and CoEL |
| Continue to strengthen our support in line with the principles of Self Directed Support and direct Carers to advice on SDS and managing personal budgets through Lothian centre for Inclusive (LcIL) Living | Process to improve access to individual budgets in place Nov 2024. Link officer for LcIL encouraging early referrals from social work to support individuals with their rights around Self Directed Support. Updated information on Self Directed Support here: https://www.eastlothian.gov.uk/info/210702/social_care/12855/organising_social_care/2 | ELHSCP, SDS improvement plan |
| Ensure Young Carers needs are considered in SDS awards | Issue raised in meetings with Social Work Colleagues. Increasing integrated working with children services through Service and Practice Development Officer. Children and disability team carry out whole family assessment process | ELHSCP, SDS improvement plan |
| Consider options for ensuring smoother transitions between services for Young Carers becoming Young Adult Carers (typically 18-25) | Need identified at impact assessment session on commissioning process Increased joint working and intergenerational events to introduce YC to adult carer support organisation Specialist support required at this transition, funding agreed to Bridges project to continue their Young Carer support role. Carers organisation considering how to increase offer of support to this group | ELHSCP Young Carers Service, CoEL and ELHSCP Carer support |
| Consider options for increasing presence of Carers representatives and information at point of diagnosis for different conditions | Carers pathway OT was looking at opportunities but significant period of vacancy in this role so minimal progress. | ELHSCP and partner organisations |
| Research how other Local Authorities are supporting carers with end of life care planning, for the cared for person and for themselves. | Key outcome of Planning for an Ageing Population engagement work was around palliative and end of life care, the Integration Joint Board accepted these recommendations in full in February 2025 and work will be taken forward by the palliative care strategy group and in line with the National strategy “Palliative Care Matters for all” Full report available here file:///C:/Users/burtm1/Downloads/2025_02_20___Planning_Older_Peoples_Services___Final_Report%20(2).pdf |  |

| Outcome 3: Carers are supported to maintain their own physical, emotional and mental wellbeing |  |  |
| --- | --- | --- |
| We said | We did | Who/Co-ordinator |
| Improved promotion of ACSP’s and YCS’s, promoting the Carers Right to these | Work to change culture, ACSP as the carers right and a tool to explore what matters to the carer not as a request for service. Introduction of new form has supported this ‘good conversation’ Video made as part of Carers Rights Day 2024 highlighting right to an ACSP/YCS | ELHSCP, CoEL, Young Carers Service |
| Support carers to promote their own health through ACSPs or YCSs and regular reviews | Good conversation can help carers prioritise their own health and well being. YC Statement and Review had a number of questions to promote discussion, reflection and personal action planning around YC own health. | Carers Strategy Officer, Young Carers Service |
| Audit of completed ACSP’s | Audit process in place with CoEL Information submitted to Scottish Government under carers census | Carers strategy officer and CoEL |
| Complete assessment/mapping of local groups, peer/buddy support and activities to assess where there are gaps in terms of conditions/areas. Respond appropriately to address isolation amongst carers through more local groups, peer/buddy support and activities. | Carers of East Lothian offer a comprehensive range of opportunities for peer support across the geographical area and with a focus on different groups such as parent carers and men who care. They listen to suggestions around different groups and respond where demand exists and resource allows. Increasing collaboration with different groups such as MILAN (senior welfare organisation | Carers Strategy Officer |
| Work with individuals to ensure that the level and nature of care provided by young carers remains appropriate for their age | YC Statement asks specific questions around YC willingness and ability to care and any concerns are raised with Children’s Services. | Young Carers Service and ELC Children’s Services |
| Continue to review East Lothian Rehabilitation Service’s new direct referral pathway for Carers to access an Occupational Therapy assessment in their own home | Vacancy in this pathway has meant pause on referrals. Service considering how group support could facilitate delivery to more carers at an earlier stage. | East Lothian HSCP rehabilitation service |
| Liaise with local partners around what is offered to carers in terms of support around grief and loss | CoEL secured funding to work with bereavement support services to support delivery of two sessions per month, on in Musselburgh and one on Tranent |  |
| Monitor demand for CoEL counselling services | 24 carers accessed counselling services in the last 6 month period, with CoEL allocating further funding from Shared Care Scotland to increase sessional counselling and reduce wait time for counselling | Carers Strategy Officer |
| Promote carers employability needs in appropriate groups and highlight new local employability structure | Local Employability Partnership restructure. East Lothian Works good relationship with Carers organisation and agreed inclusion of carers in promotional materials to highlight available support. Think Carer session delivered to East Lothian Works staff team. | Carers Strategy Officer, Local Employability Partnership |
| Employability for Young Carers | Young Carers Service co-ordinator a member of East Lothian Youth Employment Group, a subgroup of the Local Employability Network |  |
| Review training available to HSCP managers to better support staff who juggle work and unpaid caring roles | NHS Lothian take a trauma informed approach and make use of a carer passport for employees so carer situation is understood and doesn’t have to be repeated if there is for example a change of personnel or role. Practice shared with ELC Human Resources staff, would need adopted by Council Management Team |  |
| Continue to develop materials to support Young Carers in schools | Ongoing |  |
| Help young carers secure the use of their own rights under additional support for learning legislation via the service My Rights, My Say. | Ongoing | Young Carers Service |
| Support Young Carers who are eligible for Education Maintenance Allowance (EMA), Young Carers Grant and Young Scots Young Carer Packages | Supported YC to apply for YC grant. Schools supported YC to apply for Education Maintenance Allowance. All services encouraged Young Carers to apply for Young Scot YC Package. YC Service worked with Young Scot colleagues to improve application process. | Young Carers Service, Education and partner organisations |
| Provide Young Carers with free Enjoy Leisure membership and active school activities | 470 YC benefitted from free enjoy leisure membership and all school aged Young Carers had the option to attend any Active School Activity |  |
| Young Carers are prioritised by local mental health support services | Agreed Young Carers to be priority group but asking Mental health team for evidence. |  |
| Continue to look for new and varied ways of supporting carers well-being to enjoy time alone or with friends and family | Extended the range of opportunities to available to YC and negotiated for key providers to offer discounts or free places. These include Fostering Compassion, Karele, Dukes Art School and Wilder. | ELHSCP, Young Carers Service and CoEL |

| Outcome 4: Breaks from caring are timely and regularly available |  |  |
| --- | --- | --- |
| We said | We did | Who/Co-ordinator |
| Raise the profile of the importance of breaks from caring in supporting people to stay at home for longer | Communications have focused on creative and flexible breaks and increasing opportunities for breaks from caring by supporting local organisations such as Venturing Out, MILAN and Circle Focus on language and full range of opportunities for breaks, time for yourself, to do something you enjoy or to rest. | ELHSCP, CoEL, Corporate Communications team |
| Review replacement care guidelines within social work to ensure these are applied consistently giving equity of service and consider Young Carers needs | Replacement care policy published along with impact assessment report. Link to carers eligibility criteria and individual budget next step. Development needed to include consideration of Young Carers needs | Carers Strategy Officer and adult wellbeing |
| Consider Young Carers needs in relation to replacement care and access to SDS options | See above | Carers Strategy Officer and YCS coordinator |
| Monitor innovative solutions to ‘breaks from caring’ through participation in Shared Care Scotland’s promoting variety programme and Health Improvement Scotland events | Ongoing | Carers Strategy Officer |
| Continue to fund specialist short breaks support for carers so that all carers have access to information and advice on breaks from caring | Increased funding from HSCP agreed and available through Carers of East Lothians Time for me grants. | Carers Strategy Officer/ Building better breaks advisory group |
| Develop brokerage support around breaks from caring |  |  |
| Launch respitality offers to carers | East Lothian has the 4th highest number of carers who benefited from a Respitality break during 2024 despite being one of the smallest local authority areas and only joining the scheme in June Respitality impact report available here: https://www.respitality.org.uk/news/2025/04/respitality-impact-report-2024/ | CoEL Building Better Breaks worker |
| Increase access to personal budgets within the partnership to provide creative breaks from caring | Process agreed in November 2024 to increase access to individual budgets through East Lothian HSCP but minimal requests as CoEL very successful at accessing funding through time for me and Carers trust grants (since early 2025). Further work required in ensuring carers have access to personalised, flexible support in their own right. | Carers Strategy Officer and ELHSCP |
| Pursue options to increase availability of bookable residential respite to give break to carers who need this level of support | Care home link officer works with all existing and new providers to encourage provision of bookable respite. Discussions ongoing with one provider around development of a dementia specialist respite service in East Lothian | ELHSCP |
| Continue to support the development of ‘Meeting Centres’ in Musselburgh and throughout East Lothian to offer support to people with dementia and their carers | Development project ongoing until March 2026. Musselburgh Meeting centre well established although lack of pathway for ongoing support without a day centre for older people meaning meeting centre supporting more complex needs than intended. Development work ongoing in Prestonpans and Haddington | ELHSCP and DfEL |
| Keep working with our existing day services, for older people, to expand the range of services on offer to support breaks from caring | Most centres now offering blended model of day service including community Outreach focused on carer support. Short pilot in Tranent not taken forward at this time Supporting Ormiston to look at how they will offer this model | ELHSCP and East Lothian day centres for older people |
| Develop a day service in Musselburgh where there is an identified gap in provision | Integration Joint Board agreed funding for this in 2023 but asked to cease in 2024 due to financial recovery process. Impact assessment showed significant negative impact so process instead paused. Link officer been working with community on proposal for integrated model, final decision from IJB expected May 2025 | ELHSCP |
| Promote our Shared Lives scheme and continue to try and attract new paid Carers to this programme | Local campaign successful in attracting 3 new shared lives carers in Dunbar. No further locally targeted campaigns planned at this point but considered the best way of attracting new carers to the scheme. | ELHSCP Shared lives co-ordinator and team |
| Report on services outwith identified carers budget that directly support carers needs, to better understand full picture in terms of provision to meet carers needs | Repurchasing through adult social work information system to identify resource supporting carers in terms of replacement care | ELHSCP |
| Monitor numbers of Young Carers accessing breaks through opportunities and continue to expand the range of opportunities available in response to Young Carers feedback. | Numbers of YC accessing breaks is rising and that range offered is a direct result of consultation with YC Advisory group and other YC feedback. | Young Carers Service |
| Support young Carers to attend the Young Carers Festival | 15 YC attended overnight in Aug 2024 | Young carers service |
| Seek out new sources of Free Break from Caring Opportunities for Young Carers | Secured New opportunities from Fostering Compassions, Karele, Dukes Art School and Yarrow Cookery School. | Young Carers service |

| Outcome 5: Carers are supported to have a life outside of their caring role and can achieve a balance between caring and other aspects of their lives |  |  |
| --- | --- | --- |
| We said | We did | Who/Co-ordinator |
| What we will do for Adult Carers |  |  |
| As part of planning process have more open and honest conversations about what is possible and what will meet individual outcomes | Continues to improve joint working between carer support organisations and ELHSCP so carers feel supported through the process of accessing further support | ELHSCP and CoEL |
| Review numbers of carers accessing personal budgets to meet their personal outcomes | Community Care Worker reviewing all ACSP’s shared with partnership and supporting carer through process of accessing personal budget or support for cared for person. Number of personal budgets directly to meet carers needs (not through support to cared for person) remain very low, process introduced in Nov 2024 to encourage agreement to more flexible and creative use of budgets from ELHSCP, however CoEL access to Carers Trust grants at same point has meant they have been able to access more funding for carers through this route (up to £70,000 per year) |  |
| Review application of eligibility criteria to carers needs with preventative support in mind | Completed with input from around thirty carers, eligibility criteria published here https://www.eastlothian.gov.uk/downloads/file/27361/eligibility_criteria_for_carers Ongoing work to link eligibility criteria to indicative budget for support | ELHSCP and partners |
| Support carers in employment by increasing awareness of carer specific issues through the local employability partnership o Access to advice and information o Promoting the achievement of Carer Positive Status across local employers o Promotion of flexible working policies that can support carers | Advice and information through East Lothian Works Difficulty attracting businesses to find out about carer positive, start with businesses engaged through offer of breaks or activities and build on this. Legislation supports promotion of flexible working to support carers but more work needed to hear carers experiences of local employers. | ELHSCP, carers orgs and employment support services |
| Increase numbers of ‘Carer positive’ employers, encourage training opportunities for Young Carers and sign up to The Young Carers Covenant | Carer positive sessions offered as part of carers week and when promoted through Carer Positive national events. Low uptake from businesses, need to promote benefit to business. Report prepared and awaiting approval from CSP for it to go to Committee regarding ELC signing Carers covenant | ELHSCP, Young Carers Service |
| Develop carer positive checklist for small/medium employers | Carer positive advised minimal evidence required for ‘engaged’ status and would suggest this is suitable even for small businesses. | Carers strategy officer |
| What we will do for Young Carers |  |  |
| Work with schools to improve identification of young carers and to ensure both a flexible and understanding approach towards young carers needs and the provision of appropriate and tailored support | Data from YC Statement shows that the majority of YC feel their schools understand their caring role and they have someone within school that they can talk to. Knox Academy is proud to be the first school in East Lothian to achieve the We Care; Schools for Young Carers, ‘We Recognise Care’ Award. | Young Carers Service, Education and partners |
| Work with social work services to ensure that the cared-for person is in receipt of appropriate support (from either Adult or Children’s services) to both protect young carers from age inappropriate caring roles and to enable them to have a life outside their caring role | Worked closely with social work and other services supporting families to ensure our most vulnerable YC receive the right support at the right time. | Young Carers Service, Children’s Services |
| Develop services to provide specific transitions support for older young carers as they enter adulthood and to achieve and sustain positive destinations outside of their caring role | Have worked with Skills Development Scotland and East Lothian Works staff to ensure YC are part of the “No-one left behind” monitoring and support provision. | ELHSCP and partners, CoEL, bridges |

| Outcome 6: Carers are respected by professionals as ‘Partners in Care’ and are appropriately included in the planning and delivery of both the care and support for the people they care for and services locally |  |  |
| --- | --- | --- |
| We said | We did | Who/Co-ordinator |
| Continue to deliver ‘think carer’ training sessions to staff and promote new NHS Education for Scotland Equal Partners in Care training modules | 6 Think Carer sessions delivered in 2024/’25 including East Lothian Works, Enjoy Leisure and Musselburgh Citizens Advice Bureau. Developing ‘bite size’ input that can be delivered for example at team meetings reducing non attendance due to service pressures. Equal Partners in care modules hosted on TURAS and open to anyone, promoted through workforce development but unable to make these mandatory for staff and can’t gather statistics on completion from TURAS. | ELHSCP and NHS Lothian |
| Encourage Education Staff to complete Education Scotland Young Carer Personal Development Modules | Continue to promote this at every opportunity. | Young Carers Service |
| Raising awareness with professionals so every interaction is an opportunity to treat carers as partners in care | Through Think Carer and Equal Partners in care education programmes and informally by staff through attendance at local forums and groups. |  |
| Review the extent that carers are treated as partners in care within ACSP and YCS and feed back to services results from these | As part of 6 monthly audit |  |
| Identify key HSCP services and discuss appointment of Carer Champions, continue to encourage schools to identify Young Carer Champions | No official carer champion programme has been developed. Carers OT pathway has been key to raising the carer agenda in NHS teams A number of schools have a Young Carers Champion providing additional support to YC. |  |
| Identify training available for carers on the conditions effecting the people they support and how to offer appropriate support and any other identified areas | Opportunities for training shared through ELHSCP and CoEL social media. CoEL collect data on requests for training and deliver a diverse range of education opportunities including trauma informed parenting and crisis handling awareness. Carers linked to national sources of support and information where condition specific education not available locally. |  |
| We will support carers to have a have a say in the development t and delivery of services in East Lothian by: o Maintaining the standards for engagement set out in our Engagement policy o Ensure that carers are both represented and supported to be involved in the HSCP strategic groups o Engage with CoEL “Carers Voice” group on service planning and delivery: o Increase avenues for Young carers feedback including the Young Carers Forum | Ongoing Carers organisation gathers views to feed into improved impact assessment process, for example ELHSCP transport policy which was updated based on this feedback Following completion of the Planning for an ageing population, creation of the independent community panel was recognised as a key success in this process and this group is exploring how it might continue with a more general purpose around community health and social care planning, key members include chief executive of CoEL. CoEL’s Carers panel and the Young Carers Forum have been a key engagement partner in strategy development and updates. |  |
| Ensure through Service Specifications that all registered and HSCP care services capture feedback from carers as well as from users of services and have forums to engage with key stake holders | Ongoing |  |
| Plan awareness raising events for Carers week | June – annually This campaign has been growing year on year, referrals to CoEL were double the average in this week 2024 |  |
| Play an active role in local Health and wellbeing groups | Ongoing Strategic planning and commissioning officers are allocated to each area Health and Well being Group | ELHSCP, Planning and performance team |
| Work with community organisations to share information | Through contract monitoring. HSCP broadening internal ‘Comms connected’ newsletter to include many community partners, promoting regular information sharing with local communities, HSCP section included in CoEL newsletter | ELHSCP |
| Facilitate relationships between 3rd sector organisations and carers | Good examples include; Mental Health Partners Group and Children, young people and families forum. | ELHSCP |
| Promote positive role of social work to promote understanding and engagement | Improvements to social work public facing online materials. | ELHSCP |
| Work with Community Learning and Development team to highlight carers needs within the learning and development plan for 2024- 27 | https://www.eastlothian.gov.uk/downloads/download/13503/community_learning_and_development_plan The plan does not reference unpaid carers specifically but identification of vulnerable groups and learning opportunities for all. Link is through East Lothian Works who are leading on much of this work. |  |
| Increase avenues for Young Carers feedback, including the young carers forum | Ongoing | Young Carers Service |

| Outcome 7: Local communities are supported to be Carer friendly |  |  |
| --- | --- | --- |
| We said | We did | Who/Co-ordinator |
| Work within communities to raise awareness of carers, referral pathways and their need for support. | Through forums and groups, work in this year around carers rights in supporting people with mental health problems. Mental welfare commission now include community mental health teams in inspection process and emphasise need for carer involvement. Locally, carer focus in mental health partners group session and inclusion of carers in planning for Single Point of Contact for mental health services. | ELHSCP and carers organisations |
| Plan and support Carers week events | Annually, info above. | ELHSCP, Strategy officer and Corporate Communications |
| Develop and distribute information for carers in spaces carers spend time | Ongoing Development of information hubs being led by public health, carer information key aspect |  |
| Encourage the development of local peer and buddy groups for carers | Ongoing New developments include; CoEL Men Who Care, MILAN senior welfare organisation peer support group and Venturing Out, outdoor adventure group | ELHSCP and partners |
| We aim to make accessing information and support easier and more streamlined by: • Joining the dots between community services • facilitating the relationships between third sector organisations and carers • Working with community organisations to share information | By attending local forums and groups links are made between organisation supporting carers and opportunities for increasing carer awareness are taken | Carers strategy officer and carer support teams |
| Identify large local businesses to encourage to work towards Carer Positive status. | Local businesses invited to Carer positive information sessions. CoEL joined chamber of commerce to try and engage local businesses Information shared with local businesses through economic development newsletter during carers week 2024. | Carers Strategy Officer |
| Discuss progressing East Lothian Councils Carer positive status from engaged to established. Sign up to the Young Carers Covenant would support this | ELC not progressed Carer Positive agenda in this year, accredited at engaged level. Report on the Young Carers Covenant awaiting approval from Children’s Strategic Partnership for it to go to Committee | ELC |
| Promote the role of Volunteer Centre East Lothian as our Third sector interface and continue to support their ‘Community First’ community support model | Community First key to pilot project through Care at Home locality project, findings reported to care at home Change board early 2025. Care at Home strategy should set out how community support promotes early intervention and prevention reducing the need for more formal supports. | ELHSCP and VCEL |
| Support Dementia Friendly East Lothian in their aim to make our communities great places for people with Dementia and their carers to live, visit and work in | Development project around meeting centre model has focused on Musselburgh but exploring development in Prestonpans and Haddington. Challenge has been identifying people early to offer support based on the adjusting to change model | ELHSCP and DfEL |

# Glossary of terms

| Abbreviation | Full text |
| --- | --- |
| ACSP | Adult Carer Support Plan |
| C&YP | Children and Young People |
| CoEL | Carers of East Lothian |
| DfEL | Dementia Friendly East Lothian |
| ELC | East Lothian Council |
| ELCHASE | East Lothian Care Home Assessment and Support Team |
| ELHSCP | East Lothian Health and Social Care Partnership |
| EMA | Education Maintenance Allowance |
| ID | Identification |
| LGBT | Lesbian Gay Bisexual Transgender |
| SDS | Self Directed Support |
| VCEL | Volunteer Centre East Lothian |
| YC | Young Carer |
| YCS | Young Carer Statement and Young Carers Service |
| UNCRC | United Nations Convention on the Rights of the Child |